## Sheet1
CARPE MONITORING MATRIX |  |  |  | CARPE WORKPLAN |  |  |  | BUDGET BY ACTIVITY
USAID PERFORMANCE INDICATOR | NGO LANDSCAPE INDICATOR DEFINITION AND UNIT OF MEASUREMENT | DATA SOURCE | BENCHMARK | ACTIVITY CATEGORY (SUMMARY) | PLANNED TASK | RESPONSIBILITY |  | USAID FUNDS YEAR 1- WWF | USAID FUNDS YEAR 1- WCS | MATCH FUNDS YEAR 1- WWF | MATCH FUNDS YEAR 1- WCS | TOTAL YEAR 1
|  |  | Annual |  | 10/03-9/04 | NGO | PERSON
SO: Reduce the rate of forest degradation and loss of biodiversity through increased local, national, and regional natural resource management capacity in nine central African countries |  |  |  | SO: Reduce the rate of forest degradation and loss of biodiversity through increased local, national, and regional natural resource management capacity in nine central African countries
Ind 1: Forest Area (in landscapes, and surrounding areas for control/ comparison) by condition: intact/pristine; modified/degraded, secondary; non-forest (natural or cleared) | Not Required for Year One
Ind 2: Biodiversity indicators -- selected “indicator” species such as: wide-ranging “landscape” species and/or ecological keystone species (such as elephants) and/or globally threatened species (such as bonobos, lowland gorillas, etc)
Ind 3: . Forest Fragmentation or intactness in PAs and permanent forest areas within landscapes – roads may be indicator
IR 1: Natural resources managed sustainably |  |  |  | IR 1: Natural resources managed sustainably |  |  |  | SUB TOTAL IR 1
Ind 1: Percentage of area of landscapes and other focal areas covered by integrated land use plans | 1) Landscape-scale master plan developed and endorsed by all stakeholders 2) Consensus and common vision built among key stakeholders | Reports and minutes of meetings on landuse planning process. Quality of integration and participation in each planning process assessed by third-party (e.g. consultants) assessments or evaluations. Consultancy report. Maps. Partners reports provide information on such management plans within use zones (parks & PAs, CBNRM areas, forestry concessions, etc.) | 1) 5 Stakeholders meetings held with local elites, local communities, private sector in northern sector of park and buffer. 2) Socio economic assessment carried out for northern sector of Park and buffer. 3) local authority structure within Iyalima better understood. 4)Initial land-use maps for northern region produced. | In collaboration with ICCN/COCOSI members conduct a participatory land-use process assessment including socioeconomic conditions, resource use and land tenure rights | 1) Undertake biological and social surveys of Salonga (north sector) and buffer 2) Conduct Ecological Research targeted at keystone species (Pan paniscus) and habitat protection as a component of land-use planning conservation scenario desig 3) hold meeting with stakeholders to negotiate land uses 4) outline a general lands use plan for landscape based. 5) outline draft master plan. | WWF,WCS, ZSM | WWF Principal Technica Advisor, WCS-Omari, ZSM, Program Director | 180382 | 15000 | 34214 |  | 229596
Sub IR 11: Network of national parks and protected areas established and maintained in landscapes
2. management or maintenance effectiveness “Score Card for Parks” (WWF & Parks Watch); or Dudley and Stolton methodology | The overall percentage of Salonga landscape without bush meat hunting is stabilized or has increased compared to levels at Year 1 through an effective law enforcement system and collaborative management schemes with the private sector and communities | Monitoring data and reports. Law enforcement data. | 3 Law Enforcement Training workshop completed; Research station and patrol post established; Year 2 UNESCO payments to guards made; analysis of guard force and rotation plan completed; park boundaries recognized by stakeholders. Population census completed to (Boleko Wafania) to determine basis for elaborating accords (local vs/immigrant population). | Establish and provide support to build the organizational, and technical capacity of the park, specifically an effective management systems, inluding staff training, paramilitary training, equipment and infrastructures | WWF: 2.1.Provide law enforcement training, including analyses of strategic patrol around Salonga NP. 2.2. Provide daily support to operation of park and wildlife authorities, including training and equipment of park staff and guards. ZSM: 2.3 Provide Infrastructure support at Watsi-Kengo. 2.4. Provide law enforcement training at Boende. 2.5. Provide support for effective operation of park authorities through UNESCO prime deliveries. WCS: 2.6. Begin physical demarcation of Salonga NP. 2.7. Build Patrol post on Lokolo, south east of Boleko. | WWF,ZSM, WCS | WWF PTA, ZSM (PD), WCS: Jose Illanga | 188581 | 140000 | 3911 | 60000 | 392492
Sub-IR 1.2 Local community management of forests, other NRs, and sustainable agriculture benefits local livelihoods |  |  |  | Sub-IR 1.2 Local community management of forests, other NRs, and sustainable agriculture benefits local livelihoods
Sub-IR 1.3 Logging concessions are managed for sustainability |  |  |  | Sub-IR 1.3 Logging concessions are managed for sustainability
IR 2: Natural resources governance (institutions, policies, laws) strengthened |  |  |  | IR 2: Natural resources governance (institutions, policies, laws) strengthened |  |  |  | SUB TOTAL IR 2
Ind 1: Number of landscapes (or other focal areas) in which an integrated multi-sectoral national land use planning process is a) convened, b) completed, and c) implemented, under an agreed upon/legal framework | Number of initiatives catalyzed by landscape coordination Committee (COCOSI) | 1. Partners and governments/ICCN reports | at least 3 COCOSI meeting held in Year 1, with participation of stakeholders operating within the park as well as outside of the park | Strengthen local and national effective input of all stakeholders in national land use planning and enforcement process | Strengthen the capacity of CoCoSi in the Salonga landscape by including private sector and local communities, and facilitate stakeholder participation in law enforcement activities:steps include, formation of COCOSi, hold 3 CoCoSi meetings in year 1, COCOSI participates in COCOCONGO | WWF, WCS | WWF PTA | 8199 |  |  |  | 8199
Sub-IR 2.1 Policies and laws support protected areas, sustainable logging, and other sustainable NRM |  |  |  | Sub-IR 2.1 Policies and laws support protected areas, sustainable logging, and other sustainable NRM
Sub-IR 2.2 Policies and laws support CBNRM, decentralization, and local-level management |  |  |  | Sub-IR 2.2 Policies and laws support CBNRM, decentralization, and local-level management
Sub-IR 2.3 Civil society and NGO sector capacity to engage in advocacy and pressure governments to prevent illegal and/or unsustainable exploitation of resources is strengthened |  |  |  | Sub-IR 2.3 Civil society and NGO sector capacity to engage in advocacy and pressure governments to prevent illegal and/or unsustainable exploitation of resources is strengthened
Sub-IR 2.4 Regional multi-national institutions and policy coordination increased |  |  |  | Sub-IR 2.4 Regional multi-national institutions and policy coordination increased
Sub-IR 2.5 Human resources for improved natural resources governance are |  |  |  | Sub-IR 2.5 Human resources for improved natural resources governance are
1. # of national training programs at given standard of expertise for natural resources professionals (foresters, wildlife managers, etc.) 2. level of training of staff of relevant national agencies (for NGOs see sub IR 2.3 above) 3. # of training programs and ed. levels of journalists and media staff engaged in environmental reporting 4. training for politicians on environmental issues and environmental governance | # of trained staff, Technicians and wildlife managers trained in NRM | Technical Report | At least 3 protected area staffs trained in ecological monitoring and surveillance methods, 15 guards trained, and 1 manager | Build human technical capacity for local, landscape monitoring | 1) Begin Training of Conservator in management and monitoring through on the job training; 2) conduct training program for senior wildlife staff in monitoring; 3) assess level and quality of existing guards; 4) develop training curriculm drawing from UNESCO/ICCN programs 5) conduct training for 15 guards | WWF | WWF PTA | 99297 |  |  | 0 | 99297
IR 3: Natural resources monitoring institutionalized |  |  |  | IR 3: Natural resources monitoring institutionalized |  |  |  | SUB TOTAL IR 3
\ |  |  |  | Sub-IR 3.1 Monitoring network covering region is established
Number of countries monitoring forest and biodiversity indicators using common methods so information can be shared and compared | A consolidated monitoring system in the Salonga, contributing to landscape management and develop in cooperation with the nation-wide UNESCO monitoring program for world heritage sites | Document with monitoring strategy and workplan. Database and database reports. Partnership/cooperation agreement. | All major land uses (protected areas, logging concessions, public infrastructure, human settlments, traditional and community-based natural resources use zones) identified and georeferenced into a central GIS database at the Headquarters of the project. Capacity build to map and georeference information in the GIS database, and monitoring protocols developed and implemented. MIKE inventories completed through Salonga NP | Provide support for the inventoryof existing land use data and design a plan to collect missing informations, and ensure integration of all data into a centralized GIS database. Define monitoring protocols for indictaor species and fisheries | 1) Conduct an inventory of existing land-use data and integrate them into a landscape central and ICCN database. 2) Define the most cost effective approach for collecting missing information to design a land use plan. 3) Set up a multidisciplinary team to collect complementary or missing information (biological and socio economic). 4) Produce updated thematic land use maps. 5) Produce land use zoning scenarios based on existing and collected land use data. 6) Carry out assessment mission to document baseline data on hunting, agriculture, fishing. 7) Develop monitoring strategy for fisheries and indicator species (Pan paniscus). | WWF, ZSM | WWF Principal Technical Advisor, WCS-Omari, ZSM, Program Director | 8199 | 40000 |  | 50000 | 98199
Sub-IR 3.2 Forest and biodiversity information is disseminated in forms appropriate for decision makers representing a range of stakeholders |  |  |  | Sub-IR 3.2 Forest and biodiversity information is disseminated in forms appropriate for decision makers representing a range of stakeholders
Number and diversity of reports and other information-dissemination formats | Information disseminated in accessible forms to natural resources managers, decision makers and advocacy groups | Informations available through leaflets | Document bushmeat traffic at Lokolo and Wafnia. At least one leaflet produced | Organized workshop to discuss result of bushmeat survey and harmonized strategy with other bushmeat studies in other Central African countries. Develop and implement broad-based, multi-faceted environmental information, education and communication strategy | 1)Train bushmeat survey teams, 2)hold workshop in key villages, 3) Review regional strategies on bushmeat control in light of bushmeat survey, 4)test key messages for bushmeat awareness educational programs | WWF,WCS, ZSM | WWF PTA | 8199 | 40000 |  | 30000 | 78199