## PART Qs & Section Scoring
OMB Program Assessment Rating Tool (PART)
Block/Formula Grants
Name of Program: Comprehensive School Reform (CSR)
Section I: Program Purpose & Design (Yes,No, N/A)
Questions |  | Ans. | Explanation | Evidence/Data | Weighting | Weighted Score
1 | Is the program purpose clear? | Yes | The purpose of the program is to improve student achievement by supporting the implementation of comprehensive school reform, especially in low-performing, high poverty schools | Statutory purpose: "to provide incentives for schools to undertake comprehensive school reform based upon scientifically based research and effective practices" (Section 1601 of the No Child Left Behind Act of 2001). | 20% | 0.2
2 | Does the program address a specific interest, problem or need? | Yes | With increasing numbers of schools being identified as in need of improvement, this program addresses a relevant and clearly defined problem | Currently nearly 8,700 schools nationwide have been identified as in need of improvement. | 20% | 0.2
3 | Is the program designed to have a significant impact in addressing the interest, problem or need? | Yes | Funds are for start-up costs of implementing comprehensive reform at the school level. Therefore this program provides an organizing framework to improve the use of all other State and local dollars in the school. | Early findings from the National Longitudinal Survey of Schools indicate that CSR may be helping to leverage Title I funds to undertake strategies associated with successful schools | 20% | 0.2
4 | Is the program designed to make a unique contribution in addressing the interest, problem or need (i.e., not needlessly redundant of any other Federal, state, local or private efforts)? | No | CSR is duplicative of Title I Part A of the Elementary and Secondary Education Act. This program supports comprehensive school reform, which is also the purpose of Title I schoolwide programs, and helps improve low-performing schools, which is the purpose of the State school improvement set-aside in Title I. | Title I schoolwide project statutory provisions (sec. 1114 of the No Child Left Behind Act of 2001) and State school improvement set-aside (sec. 1003 of the No Child Left Behind Act of 2001). | 20% | 0
5 | Is the program optimally designed to address the interest, problem or need? | Yes | The program design provides for formula distribution to States who then compete the funds, giving priority to lowest-performing schools which have assurance of district support for reform. No evidence indicates there is a better design for the program. This does not mean that program improvements are not needed. | Section 1604(c)(1) of the No Child Left Behind Act of 2001 requires SEAs to give priority to applications that plan to use program funds in schools identified for improvement or corrective action under section 1116 of the No Child Left Behind Act of 2001. | 20% | 0.2
Total Section Score |  |  |  |  | 100% | 80%
Section II: Strategic Planning (Yes,No, N/A)
Questions |  | Ans. | Explanation | Evidence/Data | Weighting | Weighted Score
1 | Does the program have a limited number of specific, ambitious long-term performance goals that focus on outcomes and meaningfully reflect the purpose of the program? | Yes | The program has two long-term performance goals: (1) by 2014 all students in schools that have received CSR funding will meet or exceed proficiency on State assessments in reading and mathematics; (2) by 2014 no schools that have received CSR funds will be designated as in needs of improvement. | GPRA performance report | 16.67% | 0.1667
2 | Does the program have a limited number of annual performance goals that demonstrate progress toward achieving the long-term goals? | Yes | (1) The percentage of students in schools that have received CSR funds who meet or exceed proficiency on State assessments in Reading and Math will increase by 2% annually (3% in Reading at High School). (2) the number of schools that have received CSR funds designated as in need of improvement will decrease by 2.5% annually. Education collects data from States on the performance measures. | GPRA performance report | 16.67% | 0.1667
3 | Do all partners (grantees, sub-grantees, contractors, etc.) support program planning efforts by committing to the annual and/or long-term goals of the program? | Yes | In its consolidated application each State describes how it will measure the extent to which the reforms have resulted in increased student achievement; subgrant process gives priority to schools in need of improvement. | Annual consolidated performance report from each State provides data that addresses program outcome indicators; statute requires that State conduct program evaluations and share them with the Department | 16.67% | 0.1667
4 | Does the program collaborate and coordinate effectively with related programs that share similar goals and objectives? | Yes | The program collaborates with related programs and technical assistance providers that target low-performing schools in need of improvement. These programs share similar school improvement and student achievement goals. The program also works with Education's Institute of Education Sciences to evaluate whole school reform models. | CSR co-sponsors technical assistance initiatives with student achievement and school accountability program for State staff related to both programs. Activities include co-presentations and shared publications. The program also partners with regional educational labs on technical assistance and product creation. | 16.67% | 0.1667
5 | Are independent and quality evaluations of sufficient scope conducted on a regular basis or as needed to fill gaps in performance information to support program improvements and evaluate effectiveness? | Yes | Statute requires national evaluation and a report to Congress; the Department may reserve up to 1% of the amount appropriated each year for evaluation activities. The statute requires each State to evaluate annually the implementation of reforms and measure the extent to which reforms have resulted in increased student achievement. These evaluations must be submitted to the Department.The statute also requires that each LEA evaluate the implementation of comprehensive reforms and measure the results achieved. | National Longitudinal Study of Schools (NLSS); Field-Focused Study; Longitudinal Assessment of comprehensive School Reform Implementation and Outcomes (LACIO) | 16.66% | 0.1666
6 | Is the program budget aligned with the program goals in such a way that the impact of funding, policy, and legislative changes on performance is readily known? | No | The database on CSR grantees identifies the number of awards made, the actual and average amount of awards, and the number of awards made to low-performing schools. However, the Department has not determined a direct relationship between funding levels and performance goals. |  | 16.66% | 0
7 | Has the program taken meaningful steps to address its strategic planning deficiencies? | N/A | The Department has not identified any strategic planning deficiencies related to this program. |  | 0%
Total Section Score |  |  |  |  | 100% | 83.34%
Section III: Program Management (Yes,No, N/A)
Questions |  | Ans. | Explanation | Evidence/Data | Weighting | Weighted Score
1 | Does the agency regularly collect timely and credible performance information, including information from key program partners, and use it to manage the program and improve performance? | Yes | States report information annually to the Department and provide data on grantees to a contractor for inclusion in a grantee database. Performance information provided by SEAs is used to shape technical assistance provided by program office. Program guidance is key to program management and improved performance. | The program collects information about subgranting procedures, timelines, priorities. It also collects data from States through annual consolidated report. States are now required to submit annual subgrantee evaluations to the Department of Education. | 12.5% | 0.125
2 | Are Federal managers and program partners (grantees, subgrantees, contractors, etc.) held accountable for cost, schedule and performance results? | No | The Department of Education has not instituted an appraisal system that holds Federal managers accountable for grantee performance. However, as part of the President's Management Agenda, the Department is planning to implement an agency-wide system -- EDPAS -- that links employee performance to progress on strategic planning goals. In that context, the CSR program staff have created seven common performance standards aligned with the Department Strategic Plan goals, objectives and strategies. These standards, along with an individualized work plan, dictate the performance results that will be the basis for each employee's evaluation when that system is fully implemented. If sub-grantees do not make adequate implementation progress annually, continuation funds are withheld. Grantee performance is monitored annually through review and approval of application for funds, compliance reviews and site visits. |  | 12.5% | 0
3 | Are all funds (Federal and partners’) obligated in a timely manner and spent for the intended purpose? | Yes | Federal funds are obligated July 1 as required by law. The program office provides guidance and encourages States to create subgrant competition timelines that allow subgrantees adequate time to obligate funds. States held accountable for performance results. |  | 12.5% | 0.125
4 | Does the program have incentives and procedures (e.g., competitive sourcing/cost comparisons, IT improvements) to measure and achieve efficiencies and cost effectiveness in program execution? | No | This program has not yet implemented measures and procedures to improve cost efficiency in program execution. However, as part of the President's Management Agenda, the Department is implementing and agency-wide initiative to re-evaluate the efficiency of every significant business function, including the development of unit measures and the consideration of competitive sourcing and IT improvements. |  | 12.5% | 0
5 | Does the agency estimate and budget for the full annual costs of operating the program (including all administrative costs and allocated overhead) so that program performance changes are identified with changes in funding levels? | No | Education's 2004 Budget satisfies the first part of the question by presenting the anticipated S&E expenditures (including retirement costs) for this program, which constitute 1% percent of the program's full costs. However, ED has not satisfied the second part of the question because program performance changes are not identified with changes in funding levels. |  | 12.5% | 0
6 | Does the program use strong financial management practices? | Yes | Recent agency-wide audits have not identified deficiencies in the financial management of this program; the program follows the Departmental guidelines for financial management |  | 12.5% | 0.125
7 | Has the program taken meaningful steps to address its management deficiencies? | N/A | Material internal management deficiencies have not been identified for this program |  | 0%
8 (B 1.) | Does the program have oversight practices that provide sufficient knowledge of grantee activities? | Yes | Reporting system is in place that documents grantees' distribution of funds to subgrantees. Program guidance available. State program coordinators maintain contact with program office through regularly scheduled outreach meetings and communication. | SEDL database tracks subgrant and funding distribution by school; annual evaluation submitted by States. | 12.5% | 0.125
9 (B 2.) | Does the program collect grantee performance data on an annual basis and make it available to the public in a transparent and meaningful manner? | Yes | The Department collects data annually from States, including whether the number of funded schools that have been identified for improvement has decreased. | Consolidated performance report; report to Congress (years one and three); GPRA indicators; grantee database; required submission of States' evaluation | 12.5% | 0.125
Total Section Score |  |  |  |  | 100% | 62.5%
Section IV: Program Results (Yes, Large Extent, Small Extent, No)
Questions |  | Ans. | Explanation | Evidence/Data | Weighting | Weighted Score
1 | Has the program demonstrated adequate progress in achieving its long-term outcome goal(s)? | Small extent | Performance information shows improvements in elementary school, but mixed results in middle and high schools. However, these data are self-reported, are based on responses from 26 states, and are not nationally representative. They therefore should be considered to be only a preliminary measure of the progress of CSR grantees. | Consolidated state reports | 33.34% | 0.11002
| Long-Term Goal I: | Percentage of all elementary school students in schools that have received CSR funds that meet or exceed proficiency on State assessments in reading and mathematics.
| Target: | By 2014, 100% of all students in elementary school in CSR schools will be proficient in reading and math.
| Actual Progress achieved toward goal: | Reading: 75% / Math: 74% (2001)
| Long-Term Goal II: | Percentage of all middle and high school students in schools that have received CSR funds that meet or exceed proficiency on State assessments in reading and mathematics.
| Target: | By 2014, 100% of all students in middle and high school in CSR schools will be proficient in reading and math.
| Actual Progress achieved toward goal: | Middle school - Reading: 77% / Math: 74% (2001) High School - Reading: 64% / Math: 74% (2001).
| Long-Term Goal III: | Percentage of schools that have received CSR funds that are designated as in need of improvement.
| Target: | By 2014, 0% of CRS schools will be in school improvement
| Actual Progress achieved toward goal: | 30% of CSR schools are in school improvement (2001)
2 | Does the program (including program partners) achieve its annual performance goals? | Small extent | Performance information shows improvements in elementary school, but mixed results in middle and high schools. However, these data are self-reported, are based on responses from 26 states, and are not nationally representative. They therefore should be considered to be only a preliminary measure of the progress of CSR grantees. | Consolidated state reports. | 33.33% | 0.10999
| Key Goal I: | Percent of all elementary school students in schools that have received CSR funds that meet or exceed proficiency on State assessments in reading and mathematics.
| Performance Target: | 2% annual increase
| Actual Performance: | (Base year 2000/performance year 2001) Reading: 75% proficient, 8% increase / Math: 74% proficient, 12% increase.
| Key Goal II: | Percent of all middle and high school students in schools that have received CSR funds that meet or exceed proficiency on State assessments in reading and mathematics.
| Performance Target: | 2% annual increase
| Actual Performance: | (Base year 2000/performance year 2001) Middle school - Reading: 77% proficient, 21% increase / Math: 74% proficient, 0% increase. High school - Reading: 64%, 8% decrease / Math: 74%, 13% increase.
| Key Goal III: | Percentage of schools that have received CSR funds that are designated as in need of improvement.
| Performance Target: | 2.5% annual decrease
| Actual Performance: | 3% decrease from 2000 to 2001.
3 | Does the program demonstrate improved efficiencies and cost effectiveness in achieving program goals each year? | N/A | This program does not lend itself to the development of efficiency measures that link the Federal investment to program outcomes because it's combined with a significant amount of other program dollars from the Federal, State, and local levels to achieve its goals. |  | 0%
4 | Does the performance of this program compare favorably to other programs with similar purpose and goals? | N/A | No comparable data are available for other programs. |  | 0%
5 | Do independent and quality evaluations of this program indicate that the program is effective and achieving results? | Small extent | The Department of Education evaluations of both comprehensive reform models and of this program are incomplete. Early implementation data show that the program seems to be helping to catalyzes some changes in how States think about and support school improvement efforts. However, little rigorous evaluation of evidence is available to document that comprehensive school reforms are effective interventions for improving student achievement. One study found that only 3 of 24 comprehensive approaches met the criteria for having "strong evidence of positive effects on student achievement" while another study found that 3 of the 29 most commonly used comprehensive reform models had the "strongest evidence of effectiveness." | Department of Education's NLSS (National Longitudinal Survey of Schools), consolidated State reports, Longitudinal Assessment of Comprehensive School Reform Implementation and Outcomes (data collection has not yet begun); An Educators' Guide to Schoolwide Reform (1999; American Institutes for Research); Comprehensive School Reform and Student Achievement: A Meta-Analysis (2002; Center for Reserach on the Education of Students Placed At Risk) | 33.33% | 0.10999
Total Section Score |  |  |  |  | 100% | 33%
Note on C4: This section examines the clarity of program purpose and related program design and looks at all factors including those the program or agency may not directly control but which are within the influence of the program or agency such as legislation and market factors. A clear understanding of program purpose is essential to setting program goals, maintaining focus, and managing the program. Potential source documents and evidence for answering questions in this section include authorizing legislation, agency strategic plans, annual performance plans, and other agency reports. Options for answers are Yes, No or Not Applicable.
Note on B6: 1. Is the program purpose clear? Purpose of the question: to determine whether the program has a focused and well-defined mission. Elements of a Yes answer: a Yes answer would require a consensus of program purpose among interested parties (e.g., Congress, Administration, public) and a clear and unambiguous mission. Considerations can include whether the program purpose can be stated succinctly. A No answer would be appropriate if the program has multiple conflicting purposes. Evidence/Data: evidence can include program authorizing legislation, program documentation or mission statement.
Note on B7: 2. Does the program address a specific interest, problem or need? Purpose of the question: to determine whether the program addresses a specific interest, problem or need that can be clearly defined and presently exists. Elements of a Yes answer: A Yes answer would require the existence of a relevant and clearly defined interest, problem or need that the program is designed to address. A Yes answer would also require that the program purpose is still relevant to current conditions (i.e., that the problem the program was created to address still exists). Considerations could include, for example, whether the program addresses a specific market failure. For research and development programs, a Yes answer would require identification of relevance to specific national needs, agency missions, fields of science or technology, or other “customer” needs. A customer may be another program at the same or another agency, an interagency initiative or partnership, or a firm or other organization from another sector or country. Evidence/Data: evidence can include documentation of the problem, interest or need that the program is designed to address. An example could be the number and income levels of uninsured individuals for a program that provides care to those without health insurance. For research and development programs, relevance to agency mission should be based on specific ways that the program addresses an important aspect of the agency mission. This question corresponds to Relevance criteria I.C and I.D of the R&D criteria.
Note on B8: 3. Is the program designed to have a significant impact in addressing the interest, problem or need? Purpose of the question: to determine whether the program is designed to have a significant impact that is reasonably known and can be measured. Elements of a Yes answer: a Yes answer would require that the Federal contribution and impact of the program are known and that increasing or reducing the Federal funding or intervention would have a significant impact in the context of all other factors. Important considerations include the role of state and local governments and the private and non-profit sectors and whether the program extends its impact or reach by leveraging funds and contributions from other parties. For credit programs, a consideration can include the extent to which a large number of borrowers would otherwise not have access to financial resources. For research and development programs, a Yes answer would require that the program has identified potential benefits in a meaningful, credible way. R&D benefits may include technologies and methods that could provide new options in the future, if the landscape of today’s needs and capabilities changes dramatically. While all programs should try to articulate potential benefits, basic research programs may have difficulties predicting benefits of the research. For industry-related programs, a Yes answer would also require the assessment of potential program benefits and a favorable comparison to other programs with similar goals at the agency or other agencies. Evidence/Data: evidence can include the percentage of total resources and requirements directed at the problem that come from the program and the relative impact of those resources and requirements, or the resources and behavior that the Federal contribution leverages. For research and development programs, evidence should include a summary of any benefit analysis and documentation of any independent reviews of the analysis. This question corresponds to Relevance criterion I.B of the R&D criteria. Additionally, for industry-related programs, evidence should include a summary of any comparative benefit analysis and documentation of any independent reviews of the analysis. This question corresponds to Industry-Specific criterion IV.A of the R&D criteria.
Note on B9: 4. Is the program designed to make a unique contribution in addressing the interest, problem or need (i.e., is not needlessly redundant of any other Federal, state, local or private effort)? Purpose of the question: to determine whether the program is designed to fill a defensible gap or whether it instead duplicates or even competes with other Federal or non-federal programs. Elements of a Yes answer: a Yes answer would require that the program is not redundant or duplicative of other Federal or non-federal efforts, including the efforts of state and local governments or the private and non-profit sectors. A consideration can include whether the program serves a population not served by other programs. For credit programs, a Yes answer would require evidence of the market failure/absence or unwillingness of private sector participation and an overview of the market, including all international, Federal, local, and private sector participants. For research and development programs, a Yes answer would require justification that the program provides value beyond that of any similar efforts at the agency, efforts at other agencies, or efforts funded by state and local government, private and non-profit sectors, or other counties. Justification first requires due diligence in identifying similar efforts in the past or ongoing. Evidence/Data: evidence can include the number of separate programs and total expenditures or efforts supported by those programs that address a similar problem in a similar way as the program being evaluated. For research and development programs, this question corresponds to one aspect of Relevance criterion I.B of the R&D criteria.
Note on B10: 5. Is the program optimally designed to address the interest, problem or need? Purpose of the question: to determine whether the program design is logical given the current conditions and nature of the problem and whether the design is likely to yield the intended outcomes. This question addresses many elements. Elements of a Yes answer: in this question, the burden of proof is generally on selecting a No answer since it would not be feasible to consider all possible program design alternatives. A Yes answer would require that there be no conclusive evidence that another approach would be more efficient/effective to achieve the intended purpose. A consideration could be whether the government would get the same or better outcome expending fewer total resources through a different mechanism. For example, there may be evidence that a regulatory program to ensure public safety would be more effective as a grant program. There may be evidence that a research program to improve energy efficiency would be more effective as a tax incentive. The assessment should take into account whether the program funding and activity are roughly proportionate to the scope of the problem. This element includes whether funds are divided among so many purposes or recipients that the program is unable to use or target them effectively. In the case of formula grants and loan programs, the assessment should also consider how well funds are targeted to meet the program purpose and whether funds are protected against supplantation. The examination should also consider whether the program is optimally designed in its current form or whether the design no longer makes sense due to changes in the problem. For example, if a weapons system program was intended to combat a specific threat, the assessment should ask whether the design remains optimal when the nature or magnitude of the threat has changed. This question may also address legislative factors. For example, a mandatory program assessment could consider whether the program targets the intended beneficiaries to achieve the program goal. Evidence/Data: evidence can include cost effectiveness studies comparing alternative mechanisms such as a regulation versus a grant or data on the current form of the problem.
Note on C14: This section focuses on program planning, priority setting, and allocation of resources. Key elements in this section include an assessment of whether the program has a limited number of goals that are ambitious, yet achievable, to ensure planning is strategic and focused. Whether the program incorporates flexibility in the planning process to address problems identified through performance data and periodic monitoring is also an important element of this section. Potential source documents and evidence for answering questions include strategic planning documents, agency performance plans and reports, reports and submissions from program partners, evaluation plans, budget submissions and other documents. Options for answers are Yes, No or Not Applicable.
Note on B16: 1. Does the program have a limited number of specific, ambitious long-term performance goals that focus on outcomes and meaningfully reflect the purpose of the program? Purpose of the question: to determine if focused, long-term performance planning is used to guide program management and performance. This question seeks to assess whether the program goals used are salient, meaningful, and capture the most important aspects of program purpose and mission. Elements of a Yes answer: a Yes answer would require identifying a limited number (e.g., two or three) of specific, easily understood program outcome goals that directly and meaningfully support the program's mission and purpose. This question relates to Section 1, Question 1 in Program Purpose and Design. The goals should focus on outcomes and may or may not be those developed to comply with the Government Performance and Results Act (GPRA). While most programs have GPRA goals, many of these goals do not meet the standards of a Yes. A Yes answer can also be given, if OMB and the agency have reached agreement on a limited number of long-term outcome goals that will be added to the FY 2004 GPRA plan. Output goals would only meet the standards of a Yes answer, if the program can produce sound justification for not adopting outcome goals. Goals should be set relative to an established baseline, have clear time frames and targets, and challenge program managers to continuously improve program performance. Programs should have at least one efficiency goal. In evaluating the goals, considerations can also include whether the program is serving the right clients, such as with certain mandatory programs. A No answer would be given for long-term goals that do not directly and meaningfully relate to the program’s mission, do not have clear time frames and targets, or are focused on outputs and lack adequate justification. In some instances, a program may have multiple or even competing goals. In these cases, there may be a problem in the program design or the articulation of the program, which may require more focused program goals or a realignment of a program through management or legislative changes. Agency goals should be listed in the evidence/data section of the PART. For credit programs, customer service benchmarks for timeliness and quality of service and utilization or participation rates may be appropriate long-term outcome goals. Evidence/Data: evidence will include the long-term outcome goals established by the program either in the GPRA plan or other program document or as agreed to by OMB and to be included in FY 2004 GPRA documents. For research and development programs, this question corresponds in part to Performance criterion III.B of the R&D criteria.
Note on B17: 2. Does the program have a limited number of annual performance goals that demonstrate progress toward achieving the long-term goals? Purpose of the question: to determine whether a limited number of annual performance goals have been identified that directly support the long-term goals evaluated in Question 1 of Section II above. Elements of a Yes answer: a Yes answer would require annual performance goals that are discrete, quantifiable, and measurable. Most importantly, these annual goals should measure the program's progress towards reaching the long-term goals evaluated in Question 1 of Section II above. The annual performance goals may focus on outputs and may or may not be those developed by the agency to comply with GPRA. A Yes answer can also be given, if OMB and the agency have reached agreement on a limited number of annual goals that will be included in the FY 2004 GPRA plan. Programs are encouraged to have at least one efficiency goal. If the program received a No in Question 1 of Section II above, an explanation of how annual performance goals contribute to desired long-term outcomes and purpose of the program must be provided to receive a Yes for this question. Agency goals should be listed in the evidence/data section of the PART. For credit programs, customer service benchmarks for timeliness and quality of service and utilization or participation rates may be appropriate annual goals. For research and development programs, a Yes answer would require that the program provides single- and multi-year R&D objectives, with annual performance outputs, to track how the program will improve scientific understanding and its application. Programs must provide schedules with annual milestones for future competitions, decisions, and termination points, highlighting changes from previous schedules. Program proposals must define what would be a minimally effective program and a successful program. Some long-term basic research programs may not be able to define meaningful annual outcome performance measures, aside from process measures. In such cases, these programs may use process-related measures, especially those that can be conceptually linked to long-term research goals. Evidence/Data: evidence will include the annual goals established by the program either in a GPRA Annual Performance Plan or other program document or as agreed to by OMB and to be included in FY 2004 GPRA documents. For research and development programs, this question corresponds in part to Performance criterion III.B of the R&D criteria.
Note on B18: 3. Do all partners (grantees, sub-grantees, contractors, etc.) support program planning efforts by committing to the annual and/or long-term goals of the program? Purpose of the question: to determine whether program efforts carried out by program partners also support the annual and long-term goals of the program. Elements of a Yes answer: a Yes answer would require that program managers strive to ensure that partners support the overall goals of the program and measure and report on their performance as it relates to accomplishing those goals. For example, a program that requires all grant applications to include performance measures that will help the program achieve its goals and monitor those measures would receive a Yes. If, however, a program does not through a requirement or some other means get program grantees to link their activities to the program’s goals, a No would be appropriate. The most obvious example of a partner is an entity receiving program funding. While a program cannot always control the activities of their partners, it can exert influence through a number of mechanisms. If the program received a No for both Questions 1 and 2 of Section II above, the program must receive a No for this question. In the case of regulatory programs, all regulated entities are not necessarily defined as program partners. Evidence/Data: evidence can include procedures the program uses to get partners to commit to, measure, and report on performance related to the program's goals.
Note on B19: 4. Does the program collaborate and coordinate effectively with related programs that share similar goals and objectives? Purpose of the question: to determine whether a Federal program that shares a common purpose or goal with another program(s) collaborates with the other program(s) in a meaningful way. Elements of a Yes answer: the question does not apply to every Federal program, but to programs that have interrelated, but separately budgeted for efforts. An example of interrelated Federal programs could include the shared efforts of Veterans Affairs and Medicare to provide care for aging veterans. A Yes answer would require the program collaborate with related Federal programs, and, to the extent appropriate or possible, with state, local and private programs that share a common purpose or goal as well. A Yes answer would require that the program show evidence of collaboration leading to meaningful actions in management and resource allocation. For example, the existence of a coordinating council would not by itself constitute meaningful collaboration. Evidence/Data: evidence of meaningful collaboration could include joint grant announcements, planning documents, or referral systems.
Note on B20: 5. Are independent and quality evaluations of sufficient scope conducted on a regular basis or as needed to fill gaps in performance information to support program improvements and evaluate effectiveness? Purpose of the question: to ensure program planning is informed by non-biased evaluations that are either conducted regularly or on an as needed basis to fill gaps in performance information. These evaluations should be of sufficient scope to inform program improvements and influence program planning. Elements of a Yes answer: a Yes answer would require regularly scheduled objective, independent evaluations that examine how well the program is accomplishing its mission and meeting its long-term goals. In cases where a comprehensive evaluation is unnecessary based on the known effectiveness of an intervention and performance data on the program, evaluations that fill gaps in performance information can meet the elements of a Yes answer. In addition to evaluating whether the program has achieved its goals on schedule, evaluations should include recommendations on how to improve the program's performance. To ensure the program continues to meet its goals, an evaluation may be scheduled on a periodic basis, such as every two to five years or whatever time schedule is reasonable based on the specific program, its mission, and goals. To be independent, non-biased parties with no conflict of interest would conduct the evaluation. A No answer would be appropriate for a program that has no independent evaluation or (except perhaps for basic research programs) the evaluations address process and not performance. Evidence/Data: evidence can include a plan or schedule of program evaluations and program documentation describing the type of evaluation and criteria for selecting an independent evaluator. For research and development programs, this question corresponds in part to Quality criterion II.B of the R&D criteria.
Note on B21: 6. Is the program budget aligned with the program goals in such a way that the impact of funding, policy, and legislative changes on performance is readily known? Purpose of the question: to establish whether or not the budget planning and performance planning processes are integrated. Elements of a Yes answer: a Yes answer would require effective program budgeting based on a determination of the level of financial resources needed to obtain annual and long-term goals. For mandatory programs, this question would assess whether the impact of specific legislative or policy changes on likely performance is readily known. If a program budget structure varies markedly from program goals, the impact of funding, policy, or legislative decisions on actual performance of a program is very difficult to estimate. A program fitting this description would receive a No. A program with budget planning that is not tied to performance or strategic planning would also receive a No. A Yes response indicates the budget reflects program goals and that annual budget requests are clearly derived by estimating what is needed to accomplish the annual performance measures and long-term goals. For capital assets and services acquisition programs, programs should be able to identify impacts of changes in quantities on performance. Evidence/Data: evidence can include documentation of how the budget structure reflects program goals or how the cost accounting system aligns the budget with program goals. Evidence could also include how budget requests clearly and directly support achieving performance measures and long-term goals.
Note on B22: 7. Has the program taken meaningful steps to address its strategic planning deficiencies? Purpose of the question: to determine whether the program has developed a system of evaluating the effectiveness of its strategic planning efforts and to correct deficiencies when they are identified. Elements of a Yes answer: a Yes answer would require that the program has a system for identifying and correcting deficiencies in its strategic planning process and whether the program has taken meaningful steps to eliminate the deficiencies. A program that does not review planning efforts or does not make corrections to eliminate identified deficiencies would receive a No. The question addresses any deficiencies identified in this section. However, particular emphasis should be placed on whether the program is working to adopt a limited number of specific, ambitious long-term performance goals and a limited number of annual performance goals that demonstrate progress toward achieving the long-term goals, if they do not already have these goals. Evidence/Data: evidence can include a description of how deficiencies in the strategic planning of a program are identified and corrected as well as examples of such changes.
Note on C26: This section is focused on a variety of elements related to whether the program is effectively managed to meet program goals and objectives. Key areas include financial oversight, evaluation of program improvements, performance data collection, and program manager accountability. Additionally, specific areas of importance for each program type are also explored. There are a wide range of potential source documents and evidence for answering questions in this section including financial statements, GAO reports, IG reports, performance plans, budget execution data, IT plans, and independent program evaluations. Options for answers are Yes, No or Not Applicable.
Note on B28: 1. Does the agency regularly collect timely and credible performance information, including information from key program partners, and use it to manage the program and improve performance? Purpose of the question: to determine whether the program collects and reports on performance and the performance of its partners and uses the data to inform program management, resource decisions, and program performance. Program partners are other agencies or intermediaries responsible for carrying out different aspects of the program and might include partner agencies, grant recipients, participating financial institutions, regulated bodies, and contractors. Timely performance information is information that provides an accurate picture of current performance and is current enough to be useful to manage the program. Credible performance information is information that is collected through a systematic and consistent process with periodic quality controls to confirm the validity of the data. Elements of a Yes answer: a Yes answer would require that the program agency regularly collect high quality performance data relating to key program goals and use that information to adjust program priorities, make resource reallocations, or take other appropriate management actions. When key program activities are carried out by other entities, such as grantees, agencies should also consider their performance as well. A Yes also requires that the agency has collected the baseline performance data necessary to set meaningful, ambitious performance targets. For capital assets and service acquisition programs, a consideration is whether the program uses an earned value management system or similar system. Some long-term basic research programs may not be able to define meaningful annual outcome performance measures, aside from process measures. In such cases, these programs may use process-related measures, especially those that can be conceptually linked to long-term research goals. Evidence/Data: evidence can include a description of how the agency uses performance information in managing the program, as well as illustrative examples of recent management actions based on performance information. Evidence can also include steps taken by a program to enact necessary improvements cited by a specific evaluation.
Note on B29: 2. Are Federal managers and program partners (grantees, sub-grantees, contractors, etc.) held accountable for cost, schedule and performance results? Purpose of the question: to determine whether the program managers and partners are accountable for achieving program results. Elements of a Yes answer: a Yes answer would require that the program agency identify the managers who are responsible for achieving key program results and establish performance standards for those managers. When program partners contribute to the achievement of program goals, a Yes would also require those partners to achieve specific performance standards. In the case of block and formula grant programs, elements of a Yes are not confined to complying with the law. Elements of a Yes can include the presence of incentives for managers and program partners that would encourage corrections in deficient programs. For capital assets and service acquisition programs, a consideration is whether contracts include minimum performance thresholds, incentives for good performance, or other mechanisms to increase accountability. Some long-term basic research programs may not be able to define meaningful annual outcome performance measures, aside from process measures. In such cases, these programs may use process-related measures, especially those that can be conceptually linked to long-term research goals. Evidence/Data: evidence can include the use of performance management contracts with program managers, or some other mechanism for incorporating program performance into personnel performance evaluation criteria. Evidence of partners’ accountability can include requiring grant and contract awards and renewals to consider past performance.
Note on B30: 3. Are all funds (Federal and partners’) obligated in a timely manner and spent for the intended purpose? Purpose of the question: to determine whether funds are administered efficiently and obligated in accordance with planned schedules and spent for the intended purposes. Elements of a Yes answer: a Yes answer would require that the program funds be obligated consistently with the overall program plan and that a limited amount of unobligated funds remain at the end of the year. A Yes answer would also require that programs and partners establish schedules for obligations that align with the overall program plan. In addition, a Yes answer requires that adequate procedures exist for reporting actual expenditures, comparing them against the intended use, and taking timely and appropriate action to correct single audit findings when funds are not spent as intended. An important consideration for this question is whether grantees take action to address any deficiencies raised in audit reports. Evidence/Data: evidence can include periodic and year-end spending reports from the program and its partners. Evidence on expenditures can include spending reports that draw intended purpose from the Congressional Justifications, Appropriations, and program operating plans and match them against actual spending. For grantees, evidence can include grantee audit reports under the Single Audit Act, including data captured in the Federal Audit Clearinghouse, and the existence of an established procedure for reviewing actual expenditures against budgets in grant awards or appropriate Federal guidelines.
Note on B31: 4. Does the program have incentives and procedures (e.g. competitive sourcing/cost comparisons, IT improvements) to measure and achieve efficiencies and cost effectiveness in program execution? Purpose of the question: to determine whether the program has effective management procedures in place to ensure the most efficient use of each dollar spent on program execution. Elements of a Yes answer: a Yes would require that the program’s performance plans include efficiency measures and targets, such as per unit cost of outputs, timing targets, and other efficiency and productivity indicators germane to the program. A de-layered management structure that empowers front line managers and that has undergone competitive sourcing (if necessary) would also contribute to a Yes answer. For mandatory programs, a Yes could require the program to seek policies that would reduce unit costs. Evidence/Data: evidence can include performance measurements for efficiency and IT improvement plans designed to produce tangible productivity and efficiency gains, or IT business cases that document how particular projects improve efficiency.
Note on B32: 5. Does the agency estimate and budget for the full annual costs of operating the program (including all administrative costs and allocated overhead) so that program performance changes are identified with changes in funding levels? Purpose of the question: to determine whether the full costs of the program are known and are budgeted. Elements of a Yes answer: a Yes answer would require the budget estimate for the program includes all direct and indirect costs borne by the program agency, including applicable agency overhead, retirement, and other costs that might be budgeted elsewhere. While having a financial management system that fully allocates program costs and associates those costs with specific performance measures is the optimal standard, a Yes can also be achieved by having a consistent, defensible way to display the full cost of achieving performance goals. Evidence/Data: evidence can include an agency program budget estimate that identified all spending categories in sufficient detail to demonstrate that all relevant costs had been included or a report that shows the allocation of overhead and other program costs to the program.
Note on B33: 6. Does the program use strong financial management practices? Purpose of the question: to determine whether the program uses effective financial management practices in administering program funds. Elements of a Yes answer: a Yes answer would require that the program be free of material internal control weaknesses reported by auditors. Additional criteria could include whether the program has procedures in place to ensure that payments are made properly for the intended purpose to minimize erroneous payments. Evidence/Data: evidence can include recent audit reports and existence of procedures to identify and measure improper payments.
Note on B34: 7. Has the program taken meaningful steps to address its management deficiencies? Purpose of the question: to determine whether the program has developed a system of evaluating program management effectiveness and means to correct deficiencies when they are identified. Elements of a Yes answer: a Yes answer would require that the program has a system for identifying and correcting deficiencies in the various aspects of program management and implements the system to make necessary corrections. A program that does not review program management activities or does not make corrections to eliminate identified deficiencies would receive a No. Evidence/Data (if available): evidence can include a description of how deficiencies in the program management are identified and corrected as well as examples of such changes.
Note on B35: B. 1. Does the program have oversight practices that provide sufficient knowledge of grantee activities? Purpose of the question: to determine whether or not the program has an understanding of how its funds are utilized by grantees. Elements of a Yes answer: a Yes answer would require that a program have sufficient oversight capacity. This capacity may be demonstrated by a program that has a reporting system in place to document grantees use of funds in eligible activity categories, conducts site visits to a substantial number of grantees on a regular basis, audits grantee performance, and tracks actual expenditures to verify that funds are used for their designated purpose. A program with a strong relationship to its grantees and a high level of understanding of what grantees do with the resources allocated to them would receive a Yes. A program with no reporting system to track expenditures by grantees would receive a No. Evidence/Data: evidence can include the reporting structure, oversight techniques, audit or site visit schedule, and/or assess general data quality of the program.
Note on B36: B 2. Does the program collect grantee performance data on an annual basis and make it available to the public in a transparent and meaningful manner? Purpose of the question: to determine whether or not the program has a system in place to collect and present publicly information that captures the most important impacts of program performance. Elements of a Yes answer: a Yes answer would require the program collects, compiles and disseminates grantee performance information in an accessible manner, such as a web site or widely available program reports. Data would be aggregated on a program-wide level and disaggregated at the grantee level. A program would receive a No if grantee performance data are not available to the public, or if it is only aggregated at a high level. Similarly, a program could receive a No response if the data it presents are not related to the impact of the program. Evidence/Data: evidence can include citations of the types of data that are collected and disseminated as well as a description of how these data are made available.
Note on D40: This section considers whether a program is meeting its long-term and annual goals. This section also assesses how well the program compares to similar programs and how effective the program is based on independent evaluations. Potential source documents and evidence for answering questions in this section include annual performance reports, evaluations, GAO reports, IG reports and other agency documents. Assessments of program results should be based on the most recent reporting cycle or other relevant data. Answers in this section are rated as Yes, Large Extent, Small Extent, and No. Like Sections I-III, the scoring system in this section remains on a 0 to 1 point scale. Scoring for this section differs by including the option of partial credit between 0 and 1 in increments of 0, .33, .67, and 1.
Note on B42: 1. Has the program demonstrated adequate progress in achieving its long-term outcome goal(s)? Purpose of the question: to determine whether the program is meeting or making measurable progress toward meeting the goals evaluated in Question 1 of Section II. The question also seeks to determine whether the program's partners are meeting long-term outcome goals evaluated in Question 3 of Section II, if partner performance is critical to the program achieving its overall goals. Examples of partners can include grantees, participating financial institutions, regulated bodies, or suppliers. Elements of a Yes answer: a Yes answer (i.e., full credit) would require that the program meet all the goals evaluated in Question 1 of Section II. A Yes answer would not be met by simply meeting any one of its goals. A Yes answer would also require that, where applicable, partners commit to long-term outcome goals and achieve them as well. Partial credit such as Large Extent or Small Extent, should be given in cases where there is partial, but notable, achievement of goals. A program could receive a No if it received a Yes for achieving its annual goals (next question), but is not making progress toward meeting its long-term goals. Space is provided in the PART worksheet to list and document goals, targets and achieved results. If adequate goals are not available and a program received a No in Question 1 of Section II, the program must receive a No answer to this question. For research and development programs, some long-term basic research programs may not be able to define meaningful annual outcome performance measures, aside from process measures. In such cases, these programs may use process-related measures, especially those that can be conceptually linked to long-term research goals. Where appropriate, these considerations should be factored into Question 5 of this Section, which should be assessed in such a way to address the relative importance of an effective process or relevance to a field of science. Evidence/Data: evidence can include data from the agency's GPRA performance report, a strategic plan, or other Administration goals and objectives. Reports detailing customer satisfaction with program performance, program reports detailing rates of utilization or participation, or independent evaluations of the program’s performance may also be considered as relevant evidence. In cases where goals are not met, additional evidence can include an explanation of the main reasons.
Note on B53: 2. Does the program (including program partners) achieve its annual performance goals? Purpose of the question: to determine whether the program is meeting the goals evaluated in Question 2 of Section II. The question also seeks to determine whether the program's partners are meeting annual goals evaluated in Question 3 of Section II, if partner performance is critical to the program achieving its overall goals. Examples of partners can include grantees, contractors, participating financial institutions, regulated bodies, or suppliers. Elements of a Yes answer: a Yes answer (i.e., full credit) would require that the program meet all the goals evaluated in Question 2 of Section II. A Yes answer would also require the program received a Yes for Questions 1 and 2 of Section II and a Yes or Not Applicable for Question 3 of Section II. A Yes answer would not be met by simply meeting any one of its goals. A Yes answer would also require that, where applicable, partners commit to annual goals and achieve them as well. Partial credit such as Large Extent or Small Extent, should be given in cases where there is partial, but notable, achievement of goals. Space is provided in the PART worksheet to list and document goals, targets and achieved results. If adequate goals are not available and a program received a No in Question 2 of Section II, the program must receive a No answer to this question. Some long-term basic research programs may not be able to define meaningful annual outcome performance measures, aside from process measures. In such cases, these programs may use process-related measures, especially those that can be conceptually linked to long-term research goals. Where appropriate, these considerations should be factored into Question 5 of this Section, which should be assessed in such a way to address the relative importance of an effective process or relevance to a field of science. Evidence/Data: evidence can include data from the agency's annual GPRA performance report, a strategic plan, or other Administration goals and objectives. In cases where goals are not met, additional evidence can include an explanation of the main reasons. For research and development programs, this question corresponds in part to Performance criterion III.C of the R&D criteria.
Note on B64: 3. Does the program demonstrate improved efficiencies and cost effectiveness in achieving program goals each year? Purpose of the question: to determine whether management practices have resulted in efficiency gains over the past year. Elements of a Yes answer: A Yes would require that the program demonstrate improved efficiency over the prior year. Program’s that have undergone a A-76 competitions would also be eligible for yes answer, independent of the outcome. A program would normally not be eligible for a Yes answer to this question if the program received a No in Question 4 of Section III. Evidence/Data: evidence can include meeting performance targets to reduce per unit costs, meeting production and schedule targets, or meeting other targets that result in tangible productivity and efficiency gains.
Note on B65: 4. Does the performance of this program compare favorably to other programs with similar purpose and goals? Purpose of the question: to determine how well the program performs relative to other Federal programs engaged in a similar activity. Elements of a Yes answer: a Yes answer would require the program compare favorably to other Federal programs in the common measures exercise. If none of the common measures relate to the program, the user should consider relevant evaluations that allow a comparison with other Federal programs with similar purpose and goals or comparable private sector activities. If no common measures relate to the program and there are no other similar Federal programs, a Not Applicable rating would be appropriate. For capital assets and service acquisition programs, review of performance should include cost/schedule adherence, quality, and quantity of deliverables. Evidence/Data: evidence can include evaluations and documentation comparing similar programs, including, if applicable, the six common measures. For research and development programs, this question corresponds in part to Performance criterion III.C of the R&D criteria.
Note on B66: 5. Do independent and quality evaluations of this program indicate that the program is effective and achieving results? Purpose of the question: to determine whether the program is effective based on independent and comprehensive evaluations. Elements of a Yes answer: a Yes answer would require that quality program evaluations such as those measured in Question 4 of Section II indicate that the program is effective. If a program is taking necessary steps to correct deficiencies uncovered by the evaluation, the user should address this effort in Question 1 of Section III, Program Management. Relevant evaluations would be at the national program level, rather than evaluations of one or more program partners, and would not focus only on process indicators such as the number of grants provided, or hits on a web site. Relevant evaluations would consider a program's impact, effectiveness, financial management, or other measurement of performance. For research and development programs, some long-term basic research programs may not be able to define meaningful annual outcome performance measures, aside from process measures. In such cases, these programs may use process-related measures, especially those that can be conceptually linked to long-term research goals. This question should be assessed in such a way to address the relative importance of an effective process or relevance to a field of science. Evidence/Data: evidence can include findings of an evaluation conducted by the General Accounting Office, Inspectors General, academic and research institutions, agency contracts or staffs, or other entities. For research and development programs, this question corresponds in part to Relevance criterion I.E and Performance criterion III.C of the R&D criteria.