## 5000 Responses
Sample Time Estimate for Content Analysis: Medium Volume and Complexity
Assumptions
Total Responses |  |  | 5000
Forms/Letter Generator (without extra) |  | 70% | 3500
Forms/Letter Generator + extra |  | 15% | 750
Non-form |  | 15% | 750
Form pages (average 1.5 pp.) |  |  | 5250
Pages to code: Non-form & Form+ (average 2.0 pp.) |  |  | 3000
Comment Period |  |  | 90-day
Process | Staff | Description | Volume | Production Rates | Person Days
Public Response Handling
Mail Processing | Data Entry | Opening, sorting, date stamping | 5000 | 900 | 5.5556
Print emails | Data Entry | Print all emails received (est. 70%) | 3500 | 7000 | 0.5
Letter number | Data Entry | Number responses-all pages | 8250 | 2500 | 3.3
Copying | Data Entry | 2 Copies all pages (working, clean) | 8250 | 3000 | 2.75
Log responses | Data Entry | All responses | 5000 | 350 | 14.2857
Form sort | Data Entry | Sort by type | 4250 | 5000 | 0.85
Form tally | Data Entry | Data enter forms to tally | 0 | 2700 | 0
Laserfiche scanning | Data Entry | Scan pages for copy and paste | 900 | 825 | 1.0909
Scanning | Data Entry | Scan all pages for CDs | 8250 | 2100 | 3.9286
Filing | Data Entry | File responses | 5000 | 1000 | 5
Subtotal |  |  |  |  | 37.2608
Analysis and Database
Coding Structure | Team Leader | Coding structure development |  |  | 2
Team Orientation | All | Orientation and project meetings |  |  | 5
Mail ID's | Data Entry | All responses | 5000 | 200 | 25
Coding headers | Coders | All responses | 0 | 1000 | 0
Coding - 1st reads | Coders | Pages to code | 3000 | 60 | 50
Coding - QC | Coders | Second reads - 20% of pages to code | 600 | 80 | 7.5
Coding - QC | Coders | Group comment database reviews |  |  | 10
Comment Entry | Data Entry | Enter comments, coded pages | 2100 | 60 | 35
Laserfiche data entry | Data Entry | Pages laserfiche scanned | 900 | 70 | 12.8571
Header entry | Data Entry | 10-key headers (forms) | 3500 | 2700 | 1.2963
Validation | Data Entry | Validation (responses) | 5000 | 300 | 16.6667
Quality control | Data Entry | Quality control - comment entry |  |  | 1
Quality control | Data Entry | Quality control - mail ID entry |  |  | 2
Database Management | ISM | Database reports/ISM |  |  | 3
Flag Reports | Coder/Writer | Early attention/flag reports |  |  | 2
Public Concerns | Coder/Writer | Public concern identification and writing |  |  | 30
Public Concern Crosswalk | Coder/Writer | Public concern to comment crosswalk |  |  | 0
Narrative Summaries | Coder/Writer | Chapter and Executive Summary |  |  | 10
Appendices | Data Entry | Demographic appendices |  |  | 2
Edit and Publish Summary | Writer/Editor | Edit/publish |  |  | 15
CD Production | ISM | CD Production |  |  | 3
Team Management | Team Leader | Project management - all teams |  |  | 25
Subtotal |  |  |  |  | 258.3201
Total* |  |  |  |  | 295.5809
* Office supplies, paper, printing, copying, and any other non-labor expenses are not reflected here.