## HW#7 Problem #1
Homework 7-2003
56:134 Process Engineering
Posted: Oct 31, 2003
|  | Due: | Oct 6, 2003
The problem presented in this homework is identical to the one of Homework 6.
1. Schedule all activities of the processes in Figure 1 with the heuristic scheduling algorithm of Chapter 7.
2. Implement the algorithm in Excel.
3. Submit a hardcopy of the Excel computations and a disk with the Excel file.
Consider the two sub-processes shown in Figure 1 representing project approval transactions.
Figure 1. Two sub-processes representing project approval transactions.
The following data is provided:
(a) Duration of each activity is the same and equals ti = .5 hour, i = 1, …,13.
(b) The resource requirements are as follows ri1 = .4, ri2 = .6, ri3 = .5, and ri4 = .3, for all activities i = 1, ..., 13.
(c) Four types of resources are available in the quantity, R = [2, 2, 3, 3].
(d) The due dates for the activities (in minutes) are as follows: ki = 35, 65, 35, 60, 85, 90, 35, 65, 35, 35, 40, 60, 70, for i = 1, ...,13.
(e) The constant K = L = 1.
(f) The weights wi are 1, 1, 2, 3, 5, 1, 1, 6, 2, 3, 4, 7, 2, for i = 1, …, 13. | For sub-process 1 only one of the two activities 1 and 3 is performed.
(g) For sub-process 1 only one of the two activities 1 and 3 is performed.

## HW#7 Problem #1 Solution
| Calculating Reward Index | [5 empty] | Resources |  |  |  | aij = rij/Rj |  |  |  | di= pi/(SumABS(aij*bj))
Activity | Duration | Due Time | Weight | Si(t) | Vi(t) | Pi | ri1 | ri2 | ri3 | ri4 | ai1 | ai2 | ai3 | ai4 | di | Level | Rank
1 | 30 | 35 | 1 | 5 | 0.2 | 0.2 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.1414 | 1
2 | 30 | 65 | 1 | 35 | 0.028571 | 0.028571 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.0202 | 1
3 | 30 | 35 | 2 | 5 | 0.2 | 0.4 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.2828 | 1
4 | 30 | 60 | 3 | 30 | 0.033333 | 0.1 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.070699 | 1
5 | 30 | 85 | 5 | 55 | 0.018182 | 0.090909 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.064272 | 2
6 | 30 | 90 | 1 | 60 | 0.016667 | 0.016667 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.011783 | 2
7 | 30 | 35 | 1 | 5 | 0.2 | 0.2 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.1414 | 1
8 | 30 | 65 | 6 | 35 | 0.028571 | 0.17143 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.1212 | 1
9 | 30 | 35 | 2 | 5 | 0.2 | 0.4 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.2828 | 1
10 | 30 | 35 | 3 | 5 | 0.2 | 0.6 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.42419 | 1
11 | 30 | 40 | 4 | 10 | 0.1 | 0.4 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.2828 | 2
12 | 30 | 60 | 7 | 30 | 0.033333 | 0.23333 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.16496 | 3
13 | 30 | 70 | 2 | 40 | 0.025 | 0.05 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.03535 | 2
[10 empty] | Sum | 2.6 | 3.9 | 2.1667 | 1.3 | 0.011783
[7 empty] | Current Resource Status (bj) |  |  |  | b1 | b2 | b3 | b4 | Min
[11 empty] | -1.6 | -2.9 | -1.1667 | -0.3
Lets form 3 Windows
| Window 1 | 1, 2, 3, 4, 7, 8, 9, 10 |  |  | Preceding constrains
| Window 2 | 5, 6, 11, 13 |  |  | Need to ensure that X1+X3=1
| Window 3 | 13 |  |  | Therefore whenever X1 or X3 will be chosen, add 1000 to the remaining X's (X1 or X3) di
For Window 1
Iteration 1
D={ }
U={1, 2, 3, 4, 7, 8, 9, 10}
| Calculating Reward Index | [5 empty] | Resources ri1: Resources; aij = rij/Rj ai1: aij = rij/Rj | di= pi/(SumABS(aij*bj))
Activity | Duration | Due Time | Weight | Si(t) | Vi(t) | Pi | ri1 | ri2 | ri3 | ri4 | ai1 | ai2 | ai3 | ai4 | di | Level | Rank
1 | 30 | 35 | 1 | 5 | 0.2 | 0.2 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.34749 | 1
2 | 30 | 65 | 1 | 35 | 0.028571 | 0.028571 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.049641 | 1 | Min
3 | 30 | 35 | 2 | 5 | 0.2 | 0.4 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.69498 | 1
4 | 30 | 60 | 3 | 30 | 0.033333 | 0.1 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.17375 | 1
7 | 30 | 35 | 1 | 5 | 0.2 | 0.2 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.34749 | 1
8 | 30 | 65 | 6 | 35 | 0.028571 | 0.17143 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.29785 | 1
9 | 30 | 35 | 2 | 5 | 0.2 | 0.4 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.69498 | 1
10 | 30 | 35 | 3 | 5 | 0.2 | 0.6 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 1.0425 | 1
[10 empty] | Sum | 1.6 | 2.4 | 1.3333 | 0.8 | 0.049641
[7 empty] | Current Resource Status (bj) |  |  |  | b1 | b2 | b3 | b4 | Min
[11 empty] | -0.6 | -1.4 | -0.33333 | 0.2
D={2 }
|  | U={1, 3, 4, 7, 8, 9, 10} |  |  |  | Remove activity with min di from U and place it in D
Iteration 2
| Calculating Reward Index | [5 empty] | Resources ri1: Resources; aij = rij/Rj ai1: aij = rij/Rj | di= pi/(SumABS(aij*bj))
Activity | Duration | Due Time | Weight | Si(t) | Vi(t) | Pi | ri1 | ri2 | ri3 | ri4 | ai1 | ai2 | ai3 | ai4 | di | Level | Rank
1 | 30 | 35 | 1 | 5 | 0.2 | 0.2 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.49046 | 1
3 | 30 | 35 | 2 | 5 | 0.2 | 0.4 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.98093 | 1
4 | 30 | 60 | 3 | 30 | 0.033333 | 0.1 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.24523 | 1 | min
7 | 30 | 35 | 1 | 5 | 0.2 | 0.2 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.49046 | 1
8 | 30 | 65 | 6 | 35 | 0.028571 | 0.17143 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.4204 | 1
9 | 30 | 35 | 2 | 5 | 0.2 | 0.4 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.98093 | 1
10 | 30 | 35 | 3 | 5 | 0.2 | 0.6 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 1.4714 | 1
[10 empty] | Sum | 1.4 | 2.1 | 1.1667 | 0.7 | 0.24523
[7 empty] | Current Resource Status (bj) |  |  |  | b1 | b2 | b3 | b4 | Min
[11 empty] | -0.4 | -1.1 | -0.16667 | 0.3
D={2, 4 }
|  | U={1, 3, 7, 8, 9, 10} |  |  |  | Remove activity with min di from U and place it in D
Iteration 3
| Calculating Reward Index | [5 empty] | Resources ri1: Resources; aij = rij/Rj ai1: aij = rij/Rj | di= pi/(SumABS(aij*bj))
Activity | Duration | Due Time | Weight | Si(t) | Vi(t) | Pi | ri1 | ri2 | ri3 | ri4 | ai1 | ai2 | ai3 | ai4 | di | Level | Rank
1 | 30 | 35 | 1 | 5 | 0.2 | 0.2 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.83333 | 1
3 | 30 | 35 | 2 | 5 | 0.2 | 0.4 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 1.6667 | 1
7 | 30 | 35 | 1 | 5 | 0.2 | 0.2 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.83333 | 1
8 | 30 | 65 | 6 | 35 | 0.028571 | 0.17143 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.71429 | 1 | Min
9 | 30 | 35 | 2 | 5 | 0.2 | 0.4 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 1.6667 | 1
10 | 30 | 35 | 3 | 5 | 0.2 | 0.6 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 2.5 | 1
[10 empty] | Sum | 1.2 | 1.8 | 1 | 0.6 | 0.71429
[7 empty] | Current Resource Status (bj) |  |  |  | b1 | b2 | b3 | b4 | Min
[11 empty] | -0.2 | -0.8 | 0 | 0.4
D={2, 4, 8 }
|  | U={1, 3, 7, 9, 10} |  |  |  | Remove activity with min di from U and place it in D
Iteration 4
| Calculating Reward Index | [5 empty] | Resources ri1: Resources; aij = rij/Rj ai1: aij = rij/Rj | di= pi/(SumABS(aij*bj))
Activity | Duration | Due Time | Weight | Si(t) | Vi(t) | Pi | ri1 | ri2 | ri3 | ri4 | ai1 | ai2 | ai3 | ai4 | di | Level | Rank
1 | 30 | 35 | 1 | 5 | 0.2 | 0.2 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 2.7692 | 1
3 | 30 | 35 | 2 | 5 | 0.2 | 0.4 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 5.5385 | 1
7 | 30 | 35 | 1 | 5 | 0.2 | 0.2 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 2.7692 | 1 | Min
9 | 30 | 35 | 2 | 5 | 0.2 | 0.4 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 5.5385 | 1
10 | 30 | 35 | 3 | 5 | 0.2 | 0.6 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 8.3077 | 1
[10 empty] | Sum | 1 | 1.5 | 0.83333 | 0.5 | 2.7692
[7 empty] | Current Resource Status (bj) |  |  |  | b1 | b2 | b3 | b4 | Min
[11 empty] | 0 | -0.5 | 0.16667 | 0.5
D={2, 4, 8, 7 }
|  | U={1, 3, 9, 10} |  |  |  | Remove activity with min di from U and place it in D
Iteration 5
| Calculating Reward Index | [5 empty] | Resources ri1: Resources; aij = rij/Rj ai1: aij = rij/Rj | di= pi/(SumABS(aij*bj))
Activity | Duration | Due Time | Weight | Si(t) | Vi(t) | Pi | ri1 | ri2 | ri3 | ri4 | ai1 | ai2 | ai3 | ai4 | di | Level | Rank
1 | 30 | 35 | 1 | 5 | 0.2 | 0.2 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 2.093 | 1 | Min
3 | 30 | 35 | 2 | 5 | 0.2 | 0.4 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 4.186 | 1
9 | 30 | 35 | 2 | 5 | 0.2 | 0.4 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 4.186 | 1
10 | 30 | 35 | 3 | 5 | 0.2 | 0.6 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 6.2791 | 1
[10 empty] | Sum | 0.8 | 1.2 | 0.66667 | 0.4 | 2.093
[7 empty] | Current Resource Status (bj) |  |  |  | b1 | b2 | b3 | b4 | Min
[11 empty] | 0.2 | -0.2 | 0.33333 | 0.6
D={2, 4, 8, 7, 1 }
|  | U={ 3, 9, 10} |  |  |  | Remove activity with min di from U and place it in D
Iteration 6
Iteration 7
| Calculating Reward Index | [5 empty] | Resources ri1: Resources; aij = rij/Rj ai1: aij = rij/Rj | di= pi/(SumABS(aij*bj))
Activity | Duration | Due Time | Weight | Si(t) | Vi(t) | Pi | ri1 | ri2 | ri3 | ri4 | ai1 | ai2 | ai3 | ai4 | di | Level | Rank
3 | 30 | 35 | 2 | 5 | 0.2 | 0.4 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 1004.186 | 1
9 | 30 | 35 | 2 | 5 | 0.2 | 0.4 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 4.186 | 1
10 | 30 | 35 | 3 | 5 | 0.2 | 0.6 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 6.2791 | 1
[10 empty] | Sum | 0.6 | 0.9 | 0.5 | 0.3 | 4.186
[7 empty] | Current Resource Status (bj) |  |  |  | b1 | b2 | b3 | b4 | Min
[11 empty] | 0.4 | 0.1 | 0.5 | 0.7
Need to ensure that X1+X3=1
|  | D={2, 4, 8, 7, 1 } |  |  | Therefore whenever X1 or X3 will be chosen, add 1000 to the remaining X's (X1 or X3) di
|  | U={ 3, 9, 10} |  |  |  |  | Resources ri1: ALL bj are positive therefore stop
For Window 2
Iteration 1
D={ }
U={ 5, 6, 11, 13}
| Calculating Reward Index | [5 empty] | Resources ri1: Resources; aij = rij/Rj ai1: aij = rij/Rj | di= pi/(SumABS(aij*bj))
Activity | Duration | Due Time | Weight | Si(t) | Vi(t) | Pi | ri1 | ri2 | ri3 | ri4 | ai1 | ai2 | ai3 | ai4 | di | Level | Rank
5 | 30 | 85 | 5 | 55 | 0.018182 | 0.090909 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.95137 | 2
6 | 30 | 90 | 1 | 60 | 0.016667 | 0.016667 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.17442 | 2 | Min
11 | 30 | 40 | 4 | 10 | 0.1 | 0.4 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 4.186 | 2
13 | 30 | 70 | 2 | 40 | 0.025 | 0.05 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.52326 | 2
[10 empty] | Sum | 0.8 | 1.2 | 0.66667 | 0.4 | 0.17442
[7 empty] | Current Resource Status (bj) |  |  |  | b1 | b2 | b3 | b4 | Min
[11 empty] | 0.2 | -0.2 | 0.33333 | 0.6
D={6 }
|  | U={ 5, 11, 13} |  |  |  | Remove activity with min di from U and place it in D
Iteration 2
| Calculating Reward Index | [5 empty] | Resources ri1: Resources; aij = rij/Rj ai1: aij = rij/Rj | di= pi/(SumABS(aij*bj))
Activity | Duration | Due Time | Weight | Si(t) | Vi(t) | Pi | ri1 | ri2 | ri3 | ri4 | ai1 | ai2 | ai3 | ai4 | di | Level | Rank
5 | 30 | 85 | 5 | 55 | 0.018182 | 0.090909 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.34522 | 2
11 | 30 | 40 | 4 | 10 | 0.1 | 0.4 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 4.186 | 2
13 | 30 | 70 | 2 | 40 | 0.025 | 0.05 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.52326 | 2
[10 empty] | Sum | 0.6 | 0.9 | 0.5 | 0.3 | 0.34522
[7 empty] | Current Resource Status (bj) |  |  |  | b1 | b2 | b3 | b4 | Min
[11 empty] | 0.4 | 0.1 | 0.5 | 0.7
D={6 }
|  | U={ 5, 11, 13} |  |  |  |  | Resources ri1: ALL bj are positive therefore stop
For Window 2
D={ }
| Iteration 1 |  | U={12}
| Calculating Reward Index | [5 empty] | Resources ri1: Resources; aij = rij/Rj ai1: aij = rij/Rj | di= pi/(SumABS(aij*bj))
Activity | Duration | Due Time | Weight | Si(t) | Vi(t) | Pi | ri1 | ri2 | ri3 | ri4 | ai1 | ai2 | ai3 | ai4 | di | Level | Rank
12 | 30 | 60 | 7 | 30 | 0.033333 | 0.23333 | 0.4 | 0.6 | 0.5 | 0.3 | 0.2 | 0.3 | 0.16667 | 0.1 | 0.16496 | 3
[10 empty] | Sum | 0.2 | 0.3 | 0.16667 | 0.1 | 0.16496
[7 empty] | Current Resource Status (bj) |  |  |  | b1 | b2 | b3 | b4 | Min
[11 empty] | 0.8 | 0.7 | 0.83333 | 0.9
D={ }
|  | U={12} |  |  |  |  | Resources ri1: ALL bj are positive therefore stop
|  |  | Schedule Activities |  |  | Non Critical Activities | bar: Resources ri1 to Resources ri2
|  | Window 1 | 3, 9, 10 |  |  | 2, 4, 8, 7, 1 | bar: Resources ri1 to Resources ri2
|  | Window 2 | 5, 11, 13 |  |  | 6 | bar: Resources ri1 to Resources ri2
|  | Window 3 | 12 | bar: Resources ri1 to Resources ri2