## NIH Inv Bldg Sequence
2004 NIH Property Inventory - Building Sequence
This chart depicts the building sequence for the 2004 inventory.
The inventory will typically be performed Monday through Thursday, between the hours of 8:30AM and 4:00PM. Each Friday, inventory personnel will work to complete the inventory of selected areas such as rooms requiring a return visit and to check buildings as part of the building closure process. This sequence is provided for your information and planning. The progress chart below shows a projection of the week the inventory is planned to start for each of the buildings/sites in the sequence. This information is subject to change as the inventory progresses. Should changes become necessary, they will be coordinated directly with the appropriate IC personnel. In addition to updating this page as the inventory progresses, weekly emails with inventory progress and schedule updates as well as daily scheduling emails will be sent as in prior years.
NOTE: Tentative planning for remote site operations is included. Dates indicated are subject to change based on coordination with NIH.
KEY
PLANNED BUILDING
COMPLETED BUILDING
PROJECTED NEXT WEEK
LAST UPDATED: Mar 29, 2004
PLANNED BUILDING SEQUENCE |  |  |  |  | PROGRESS TO DATE
DESCRIPTION |  | SITE | NUMBER OF ACCOUNTABLE ITEMS | PROJECTED START DATE RANGE | BUILDING STARTED | 50% OF FLOORS COMPLETE | BUILDING COMPLETE
6011 EX BLVD ROCK MD |  | C | 1567 | Jan 12 - Jan 16 | Jan 12 |  | Jan 16
6130 EX BLVD ROCK MD |  | C | 2977 | Jan 12 - Jan 16 | Jan 13 |  | Jan 23
6120 EX BLVD ROCK MD |  | C | 3549 | Jan 19 - Jan 23 | Jan 20 |  | Jan 30
6116 EX BLVD ROCK MD |  | C | 3551 | Jan 26 - Jan 30 | Jan 26 |  | Feb 6
BLDG 6700A ROCKLEDGE DRIVE BETHESDA |  | B | 89 | Jan 26 - Jan 30 | Jan 28 |  | Feb 6
8424HC GAITHERSBURG MD |  | G | 270 | Jan 26 - Jan 30 | Jan 29 |  | Jan 30
BLDG T10D MAIN CAMPUS |  | A | 18 | Jan 26 - Jan 30 | Vacated by NIH
BLDG T10B4 MAIN CAMPUS |  | A | 16 | Jan 26 - Jan 30 | Jan 29 |  | Jan 30
BLDG T30A MAIN CAMPUS |  | A | 12 | Jan 26 - Jan 30 | Jan 29 |  | Feb 6
BLDG T30B MAIN CAMPUS |  | A | 6 | Jan 26 - Jan 30 | Jan 29 |  | Feb 6
BLDG T37A MAIN CAMPUS |  | A | 12 | Jan 26 - Jan 30 | Jan 29 |  | Feb 6
BLDG T40B MAIN CAMPUS |  | A | 13 | Jan 26 - Jan 30 | Jan 29 |  | Feb 6
BLDG T46B MAIN CAMPUS |  | A | 26 | Jan 26 - Jan 30 | Jan 29 |  | Jan 30
BLDG T46D MAIN CAMPUS |  | A | 8 | Jan 26 - Jan 30 | No Government Property
BLDG T46E MAIN CAMPUS |  | A | 29 | Jan 26 - Jan 30 | Jan 29
ROCKLEDGE CENTER 2 |  | B | 3596 | Feb 2 - Feb 6 | Feb 2 |  | Feb 6
ROCKLEDGE CENTER 1 |  | B | 2283 | Feb 2 - Feb 6 | Feb 2 |  | Feb 20
BLDG 6700B |  | B | 1642 | Feb 9 - Feb 13 | Feb 10 |  | Feb 20
BLDG 6610 |  | B | 1417 | Feb 9 - Feb 13 | Feb 11 |  | Feb 20
TDP TWO DEMOCRACY PLAZA BETHSD |  | B | 2971 | Feb 16 - Feb 20 | Feb 17 |  | Feb 27
BLDG 123 12300 TW PKWY ROCK MD |  | C | 49 | Feb 16 - Feb 20 | Feb 19 |  | Feb 20
PARKLAWN BLDG ROCK MD |  | C | 19 | Feb 16 - Feb 20 | Feb 19 |  | Feb 27
4949 BATTERY LN BETHESDA |  | B | 4 | Feb 16 - Feb 20 | Feb 20 |  | Feb 20
ODP ONE DEMOCRACY PLAZA BETHSD |  | B | 647 | Feb 16 - Feb 20 | Feb 19 |  | Feb 27
6001 EX BLVD ROCK MD |  | C | 4086 | Feb 23 - Feb 27 | Feb 23 |  | Feb 27
BLDG 2 MAIN CAMPUS |  | A | 578 | Feb 23 - Feb 27 | Feb 26 |  | Feb 27
WILLCO 6000 EX BLVD ROCK MD |  | C | 690 | Feb 23 - Feb 27 | Vacated by NIH
GDC GAITHERSBURG MD |  | G | 263 | Feb 23 - Feb 27 | Feb 26
6100 EX BLVD ROCK MD |  | C | 1821 | Mar 1 - Mar 5 | Mar 1 |  | Mar 5
GATEWAY BLDG BETHESDA |  | B | 716 | Mar 1 - Mar 5 | Mar 2 |  | Mar 5
BLDG 45 MAIN CAMPUS |  | A | 2310 | Mar 1 - Mar 5 | Mar 3 |  | Mar 5
BLDG 31 MAIN CAMPUS |  | A | 248 | Mar 8 - Mar 12 | Mar 8 |  | Mar 19
BLDG 31A MAIN CAMPUS |  | A | 2954 | Mar 8 - Mar 12 | Mar 8 |  | Mar 19
BLDG 31B MAIN CAMPUS |  | A | 3197 | Mar 8 - Mar 12 | Mar 9 |  | Mar 19
BLDG T46 MAIN CAMPUS |  | A | 1 | Mar 15 - Mar 19 | Mar 17 |  | Mar 19
BLDG 31C MAIN CAMPUS |  | A | 2014 | Mar 15 - Mar 19 | Mar 15 |  | Mar 19
BLDG 46 MAIN CAMPUS |  | A | 1 | Mar 15 - Mar 19 | Mar 17 |  | Mar 19
BLDG 60 MAIN CAMPUS |  | A | 12 | Mar 15 - Mar 19 | Mar 17 |  | Mar 26
BLDG 62 MAIN CAMPUS |  | A | 1 | Mar 15 - Mar 19 | Mar 17 |  | Mar 19
BLDG 64 MAIN CAMPUS |  | A | 15 | Mar 15 - Mar 19 | Mar 17 |  | Mar 19
BLDG 9 MAIN CAMPUS |  | A | 768 | Mar 15 - Mar 19 | Mar 18 |  | Mar 26
GDP 5413 CEDAR LANE BETHESDA |  | B | 105 | Mar 15 - Mar 19 | Mar 18 |  | Mar 26
BLDG 61 MAIN CAMPUS |  | A | 41 | Mar 15 - Mar 19 | Mar 18 |  | Mar 19
BLDG 61A MAIN CAMPUS |  | A | 93 | Mar 15 - Mar 19 | Mar 18 |  | Mar 19
12401 WASHINGTON AVE ROCK MD - CRYOGENICS |  | C | 92 | Mar 15 - Mar 19 | Mar 18 |  | Mar 19
BLDG BRI |  | C | 4 | Mar 15 - Mar 19 | Mar 18
TWINBROOK 2 ROCK MD |  | C | 808 | Mar 22 - Mar 26 | Mar 22 |  | Mar 26
TWINBROOK 1 ROCK MD |  | C | 612 | Mar 22 - Mar 26 | Mar 22 |  | Mar 26
BLDG 1 MAIN CAMPUS |  | A | 948 | Mar 22 - Mar 26 | Mar 23 |  | Mar 26
NAT'L NAVAL MED CTR 1 |  | B | 9 | Mar 22 - Mar 26 | Vacated by NIH
NAT'L NAVAL MED CTR 5 |  | B | 117 | Mar 22 - Mar 26 | Mar 24 |  | Mar 26
NAT'L NAVAL MED CTR 8 |  | B | 603 | Mar 22 - Mar 26 | Mar 24 |  | Mar 26
NAT'L NAVAL MED CTR 10 |  | B | 11 | Mar 22 - Mar 26 | Mar 24 |  | Mar 26
USUHS MEDICAL CENTER |  | B | 30 | Mar 22 - Mar 26 | Mar 25 |  | Mar 26
AFRI43 BETHESDA MD |  | B | 18 | Mar 22 - Mar 26 | Mar 25 |  | Mar 26
AFRI46 BETHESDA MD |  | B | 67 | Mar 22 - Mar 26 | Mar 25 |  | Mar 26
BLDG 38 MAIN CAMPUS |  | A | 2048 | Mar 22 - Mar 26 | Mar 25
BLDG 38A MAIN CAMPUS |  | A | 4768 | Mar 29 - Apr2
BLDG 6A MAIN CAMPUS |  | A | 372 | Apr 5 - Apr 9
BLDG 6B MAIN CAMPUS |  | A | 797 | Apr 5 - Apr 9
BLDG 6 MAIN CAMPUS |  | A | 1201 | Apr 5 - Apr 9 | UNDER RENOVATION
BLDG 14A MAIN CAMPUS |  | A | 338 | Apr 5 - Apr 9
BLDG 14B MAIN CAMPUS |  | A | 84 | Apr 5 - Apr 9
BLDG 14C MAIN CAMPUS |  | A | 141 | Apr 5 - Apr 9
BLDG 14D MAIN CAMPUS |  | A | 101 | Apr 5 - Apr 9
BLDG T28 MAIN CAMPUS |  | A | 23 | Apr 5 - Apr 9
BLDG 82 MAIN CAMPUS |  | A | 248 | Apr 5 - Apr 9
BLDG 40 MAIN CAMPUS |  | A | 952 | Apr 5 - Apr 9
VEHICLES |  |  |  | Apr 5 - Apr 9
BLDG 41 MAIN CAMPUS |  | A | 1414 | Apr 12 - Apr 16
BLDG 41A MAIN CAMPUS |  | A | 10 | Apr 12 - Apr 16
BLDG 4 MAIN CAMPUS |  | A | 1734 | Apr 12 - Apr 16
BLDG 14E MAIN CAMPUS |  | A | 407 | Apr 12 - Apr 16
BLDG 14F MAIN CAMPUS |  | A | 115 | Apr 12 - Apr 16
BLDG 14G MAIN CAMPUS |  | A | 123 | Apr 12 - Apr 16
BLDG 14H MAIN CAMPUS |  | A | 10 | Apr 12 - Apr 16
BLDG 21 MAIN CAMPUS |  | A | 461 | Apr 12 - Apr 16
BLDG T21 MAIN CAMPUS |  | A | 6 | Apr 12 - Apr 16
BLDG T26 MAIN CAMPUS |  | A | 6 | Apr 12 - Apr 16
PARK BLDG ROCK MD |  | C | 820 | Apr 19 - Apr 23
NSA CTRL MAIL PRINT FAC |  | C | 398 | Apr 19 - Apr 23
FLOW BLDG ROCK MD |  | C | 704 | Apr 19 - Apr 23
KEY WEST MED CTR |  | C | 412 | Apr 19 - Apr 23
ATC 8717 GROVEMONT GTHB |  | G | 1190 | Apr 19 - Apr 23
5 RESEARCH CT ROCK MD |  | C | 841 | Apr 19 - Apr 23
GUDESS 851 E GUDE DR ROCK MD |  | C | 20 | Apr 19 - Apr 23
BLDG 11 MAIN CAMPUS |  | A | 83 | Apr 19 - Apr 23
BLDG 8 MAIN CAMPUS |  | A | 1872 | Apr 26 - Apr 30
BLDG 16 MAIN CAMPUS |  | A | 88 | Apr 26 - Apr 30
BLDG 16A MAIN CAMPUS |  | A | 4 | Apr 26 - Apr 30
10401 FERNWOOD RD |  | B | 2758 | Apr 26 - Apr 30
BLDG 13 MAIN CAMPUS |  | A | 3339 | May 3 - May 7
BLDG 30 MAIN CAMPUS |  | A | 1466 | May 3 - May 7
BLDG 36 MAIN CAMPUS |  | A | 3790 | May 10 - May 14
BLDG 37 MAIN CAMPUS |  | A | 4882 | May 10 - May 14
BLDG 18 MAIN CAMPUS |  | A | 110 | May 17 - May 21
BLDG T18 MAIN CAMPUS |  | A | 58 | May 17 - May 21
BLDG 32 MAIN CAMPUS |  | A | 171 | May 17 - May 21
BLDG T32 MAIN CAMPUS |  | A | 14 | May 17 - May 21
BLDG T32I MAIN CAMPUS |  | A | 95 | May 17 - May 21
BLDG T32II MAIN CAMPUS |  | A | 170 | May 17 - May 21
BLDG 28 MAIN CAMPUS |  | A | 115 | May 17 - May 21
BLDG 28A MAIN CAMPUS |  | A | 119 | May 17 - May 21
BLDG 49 MAIN CAMPUS |  | A | 4755 | May 24 - May 28
POOLESVILLE |  | D | 103 | May 31 - June 4
BLDG 3 MAIN CAMPUS |  | A | 39 | May 31 - June 4
BLDG 7 MAIN CAMPUS |  | A | 186 | May 31 - June 4
REMOTE SITE - NC |  | K | 699 | Jun 7 - Jun 11
BLDG 15B MAIN CAMPUS |  | A | 38 | Jun 7 - Jun 11
BLDG 15C MAIN CAMPUS |  | A | ?? | Jun 7 - Jun 11
BLDG 15G MAIN CAMPUS |  | A | 41 | Jun 7 - Jun 11
BLDG 15H MAIN CAMPUS |  | A | 2 | Jun 7 - Jun 11
BLDG 15K MAIN CAMPUS |  | A | 213 | Jun 7 - Jun 11
BLDG 29 MAIN CAMPUS |  | A | 20 | Jun 7 - Jun 11
BLDG 29A MAIN CAMPUS |  | A | 122 | Jun 7 - Jun 11
BLDG 29B MAIN CAMPUS |  | A | 50 | Jun 7 - Jun 11
BLDG 10A MAIN CAMPUS |  | A | 121 | Jun 7 - Jun 11
6006 EX BLVD ROCK MD |  | C | 79 | Jun 7 - Jun 11
BLDG 22 MAIN CAMPUS |  | A | 53 | Jun 7 - Jun 11
BLDG 23 MAIN CAMPUS |  | A | 3 | Jun 7 - Jun 11
BLDG 25 MAIN CAMPUS |  | A | 4 | Jun 7 - Jun 11
SURPLUS YARD MAIN CAMPUS |  | A | 5 | Jun 7 - Jun 11
REMOTE SITE - AZ |  | H | 768 | Jun 14 - Jun 18
6101 EX BLVD ROCK MD |  | C | ?? | Jun 14 - Jun 18
REMOTE SITE - MT |  | J | 1685 | Jun 21 - Jun 25
BLDG 5 MAIN CAMPUS |  | A | 1902 | Jun 21 - Jun 25
REMOTE SITE - MI |  | M | 600 | Jun 28 - Jul 2
BLDG 50 MAIN CAMPUS |  | A | 5032 | Jun 28 - Jul 2
BLDG 12 MAIN CAMPUS |  | A | 2367 | Jul 5 - Jul 9
BLDG 12B MAIN CAMPUS |  | A | 564 | Jul 5 - Jul 9
BLDG 12A MAIN CAMPUS |  | A | 1631 | Jul 5 - Jul 9
BLDG 10 MAIN CAMPUS
| BLDG 10, FLOOR 14 | A | 161 | Jul 12 - Jul 16
| BLDG 10, FLOOR 13 | A | 818 | Jul 12 - Jul 16
| BLDG 10, FLOOR 12 | A | 1173 | Jul 12 - Jul 16
| BLDG 10, FLOOR 11 | A | 1771 | Jul 12 - Jul 16
| BLDG 10, FLOOR 10 | A | 2425 | Jul 12 - Jul 16
| BLDG 10, FLOOR 9 | A | 1878 | Jul 19 - Jul 23
| BLDG 10, FLOOR 8 | A | 1570 | Jul 19 - Jul 23
| BLDG 10, FLOOR 7 | A | 2024 | Jul 26 - Jul 30
| BLDG 10, FLOOR 6 | A | 2307 | Jul 26 - Jul 30
| BLDG 10, FLOOR 5 | A | 3105 | Aug 2 - Aug 6
| BLDG 10, FLOOR 4 | A | 2746 | Aug 2 - Aug 6
| BLDG 10, FLOOR 3 | A | 2735 | Aug 9 - Aug 13
| BLDG 10, FLOOR 2 | A | 3448 | Aug 16 - Aug 20
| BLDG 10, FLOOR 1 | A | 4052 | Aug 16 - Aug 20
| BLDG 10, FLOOR B1 | A | 2705 | Aug 23 - Aug 27
| BLDG 10, FLOOR B2 | A | 1541 | Aug 30 - Sep 3
| BLDG 10, FLOOR B3 | A | 904 | Aug 30 - Sep 3
BALTIMORE |  | E | 7102 | Sep 13 - Sep 17