## Description
Requirements Prioritization Model
Karl Wiegers
This spreadsheet contains a simple model for estimating the relative priorities of implementing
specific features or requirements in a software system. The "Example" worksheet contains an
example, from a project called the Chemical Tracking System. The worksheet called
"Template" contains several blank rows that contain all the formulas. To use this tool, copy
the "Template" worksheet into a new spreadsheet file and enter your own items to be prioritized,
copying and inserting blank rows as necessary to get enough space to handle all the items you
wish to prioritize in one pass.
The priority is considered to be a function of how desirable it is to include a specific feature
(where desirability considers both the benefit the feature would provide to the customer, and
the penalty you might incur in the customer's eyes if the feature is omitted), and both the
relative cost and technical risk associated with implementing the feature. Every proposed feature
is rated for each of the four dimensions (benefit, penalty, cost, risk) on a relative scale
of 1-9 (9 is high). You can also adjust the weighting factors for each of these four dimensions. For example,
if you feel that benefit is twice as important as penalty, which is the same importance as cost,
but risk is only half as important as cost, then you would use weighting factors (in row 1 of the
example) of 2, 1, 1, and 0.5, respectively.
After entering the relative numbers for all the features, the relative priority for each
feature is calculated by considering the percentage of the weighted feature desirability
(or value), cost, and risk attributable to each feature. If you sort the list of features
descending by the "Priority" column, the top priority items are at the top of the list.
You would not use this approach to estimate priorities for features that you know must be included,
for any reason (political, competitive advantage, regulatory or contractual requirement, etc.). Only
use this tool as a way to differentiate among requirements that are not on the list of "absolutely
must do"s.
The "Multiple Stakeholders" worksheet illustrates a refinement of the basic spreadsheet that accommodates
multiple stakeholders or user classes who have different ideas about requirement priorities. This example
handles three stakeholders. Each stakeholder has a separate pair of columns for rating benefit and penalty.
The numbers in row 1 indicate the relative weight that each stakeholder gets in the decision-making process.
Favored user classes get higher weighting factors. The spreadsheet incorporates those weights when it
calculates the overall benefit and penalty numbers for each proposed requirement. You can experiment
with the benefit and penalty values, and the weighting factors, in this worksheet to see the effect of different
stakeholder evaluations on the calculated priority numbers.
This spreadsheet is Copyright © 2002 by Karl E. Wiegers.
Permission is granted to use, modify, and distribute this spreadsheet file.
More information about the model can be found in Software Requirements by Karl E. Wiegers,
Microsoft Press 1999 (Second Edition due in 2003)

## Multiple Stakeholders
Relative Weights: | 3 |  | 1 |  | 1 |  | 1 | 1 |  |  | 1 |  | 1
| Stakeholder 1 |  | Stakeholder 2 |  | Stakeholder 3
Feature | Relative Benefit | Relative Penalty | Relative Benefit | Relative Penalty | Relative Benefit | Relative Penalty | Total Benefit | Total Penalty | Total Value | Value % | Relative Cost | Cost % | Relative Risk | Risk % | Priority
Query status of a vendor order | 7 | 3 | 5 | 3 | 5 | 3 | 6.2 | 3 | 9.2 | 9.4262 | 2 | 4.7619 | 1 | 3.0303 | 1.2097
Generate a Chemical Stockroom inventory report | 3 | 7 | 9 | 7 | 9 | 7 | 5.4 | 7 | 12.4 | 12.7049 | 5 | 11.9048 | 3 | 9.0909 | 0.60512
See history of a specific chemical container | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 10 | 10.2459 | 3 | 7.1429 | 2 | 6.0606 | 0.776
Print a chemical safety datasheet | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 3.0738 | 1 | 2.381 | 1 | 3.0303 | 0.56803
Maintain a list of hazardous chemicals | 4 | 9 | 4 | 9 | 4 | 9 | 4 | 9 | 13 | 13.3197 | 4 | 9.5238 | 4 | 12.1212 | 0.61537
Modify a pending chemical request | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 7 | 7.1721 | 3 | 7.1429 | 2 | 6.0606 | 0.5432
Generate an individual laboratory inventory report | 6 | 2 | 6 | 2 | 6 | 2 | 6 | 2 | 8 | 8.1967 | 4 | 9.5238 | 3 | 9.0909 | 0.44034
Search vendor catalogs for a specific chemical | 9 | 8 | 9 | 8 | 9 | 8 | 9 | 8 | 17 | 17.418 | 7 | 16.6667 | 8 | 24.2424 | 0.42577
Check training database for hazardous chemical training record | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 7 | 7.1721 | 4 | 9.5238 | 2 | 6.0606 | 0.46021
Import chemical structures from structure drawing tools | 7 | 4 | 7 | 4 | 7 | 4 | 7 | 4 | 11 | 11.2705 | 9 | 21.4286 | 7 | 21.2121 | 0.26431
Totals | 50 | 46 | 54 | 46 | 54 | 46 | 51.6 | 46 | 97.6 | 100 | 42 | 100 | 33 | 100

## Example
Relative Weights: | 2 | 1 |  |  | 1 |  | 0.5
Feature | Relative Benefit | Relative Penalty | Total Value | Value % | Relative Cost | Cost % | Relative Risk | Risk % | Priority
Print a material safety data sheet | 2 | 4 | 8 | 5.1613 | 1 | 2.7027 | 1 | 3.0303 | 1.2237
Query status of a vendor order | 5 | 3 | 13 | 8.3871 | 2 | 5.4054 | 1 | 3.0303 | 1.2119
Generate a Chemical Stockroom inventory report | 9 | 7 | 25 | 16.129 | 5 | 13.5135 | 3 | 9.0909 | 0.89313
See history of a specific chemical container | 5 | 5 | 15 | 9.6774 | 3 | 8.1081 | 2 | 6.0606 | 0.86883
Search vendor catalogs for a specific chemical | 9 | 8 | 26 | 16.7742 | 3 | 8.1081 | 8 | 24.2424 | 0.8292
Maintain a list of hazardous chemicals | 3 | 9 | 15 | 9.6774 | 3 | 8.1081 | 4 | 12.1212 | 0.68301
Modify a pending chemical request | 4 | 3 | 11 | 7.0968 | 3 | 8.1081 | 2 | 6.0606 | 0.63714
Generate an individual laboratory inventory report | 6 | 2 | 14 | 9.0323 | 4 | 10.8108 | 3 | 9.0909 | 0.58818
Check training database for hazardous chemical training record | 3 | 4 | 10 | 6.4516 | 4 | 10.8108 | 2 | 6.0606 | 0.46612
Import chemical structures from structure drawing tools | 7 | 4 | 18 | 11.6129 | 9 | 24.3243 | 7 | 21.2121 | 0.33246
Totals | 53 | 49 | 155 | 100 | 37 | 100 | 33 | 100

## Template
Relative Weights: | 1 | 1 |  |  | 1 |  | 1
Feature | Relative Benefit | Relative Penalty | Total Value | Value % | Relative Cost | Cost % | Relative Risk | Risk % | Priority
<List each feature, requirement, or use case to be prioritized |  |  | 0 | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0!
in these cells, one item per cell. Copy and insert additional |  |  | 0 | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0!
rows as needed; the formulas will adjust automatically.> |  |  | 0 | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0!
|  |  | 0 | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0!
Totals | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0!