## FMEA Chart
Failure Modes and Effects Analysis
Group Number: 11 |  | Date Completed: February 10, 2004
Project: Biometric Data Mining |  | Completed by: Rick Federkeil, Travis Ayers, Rajiv Parmar, Rick Federkeil
Revision No: 1
Component Description |  | Possible Failure Modes | Effects of Failure | Severity Rating | Causes of Failure | Probability of Occurrence | Controls | Effectiveness of Controls | Risk Priority Number (RPN) | Actions to Reduce RPN
Part | Function
Hardware:
Computer | Runs software | Computer crashes | User loses unsaved work | 2 | Program failure | 3 | n/a | n/a | n/a | n/a
|  | Code gets deleted | User cannot generate fingerprints | 8 | User Accident | 1 | Maintain a backup | 1 | 8 | Include backup software copy
|  |  |  | 8 | Program failure | 3 | Maintain a backup | 1 | 24 | Include backup software copy
|  | Lacks resources to run code | User experiences poor performance when running code | 4 | Insufficient computer hardware | 2 | Meet Matlab hardware requirements | 2 | 16 | Clearly indicate hardware requirements
|  |  | Causes computer to crash/freeze | 4 | Program inefficiently designed | 4 | Testing completed program | 4 | 64 | Write more efficient code
|  |  |  | 4 | Program is incorrectly using too much resources | 1 | Testing completed program | 4 | 16 | Repair bugs in programming
Server | Information storage | Hard disk fails | Program and database is lost | 7 | Overheating | 1 | n/a | n/a | n/a | n/a
[5 empty] | Defective hard drive | 1 | n/a | n/a | n/a | n/a
[5 empty] | Dust | 1 | n/a | n/a | n/a | n/a
|  | Hard disk gets maxed out (i.e. run out of storage space) | Cannot generate additional fingerprints or run the program | 2 | Fingerprint images are too big (occupy too much space) | 3 | Measure and document output image size | 2 | 12 | Re-evaluate at next FMEA
|  |  |  | 2 | User generates too many fingerprints | 3 | Include code to prompt user with warning | 3 | 18 | Place output limits in program
Matlab Program | Programming software | Matlab cannot find required functions | Program cannot run | 9 | Missing toolboxes | 5 | Document program requirements | 4 | 180 | Document for now, possibly include code to check for required functions
|  | Code is Incompatible with users matlab version | Program works sporadically | 8 | Matlab versions are incompatible | 5 | Test with different versions | 6 | 240 | Clearly indicate required software versions
|  |  | Program fails completely | 10 | Matlab versions are incompatible | 3 | Test with different versions | 6 | 180 | Clearly indicate required software versions
Software:
Image Input | Takes the fingerprint image and imports it into matlab | Program cannot load users image | Program fails when loading image | 9 | Incompatible image format | 6 | Program tests for compatible image format | 2 | 108 | Include function to test image and perform error handling
Filters | Converts greyscale fingerprint images to binary images to ease modeling | Image quality is too poor to be properly filtered | Final fingerprint is distorted | 7 | Ineffective image filtering algorithms | 3 | Test program | 9 | 189 | Test program upon completion
|  |  |  | 7 | Images are too noisy to be adequately filtered | 5 | Test program with different images | 4 | 140 | Include code to test for image quality
[7 empty] | Warn user about required image quality | 3 | 105 | Document required image quality
Modeling | Models fingerprint ridges with mathematical equations/variables, etc. | Fingerprint ridges are not correctly joined and separated after filtering | Final fingerprint is distorted and unrecognizable | 7 | Ineffective image processing | 2 | Pre-test program | 3 | 42 | Test different filtering methods
[7 empty] | Write code to test output image against expected output | 2 | 28 | Include code into design
Generation | Use modeling techniques to manipulate and create a new fingerprint | Generator makes fingerprint unrecognizable | User is unsatisfied with final product | 7 | Ineffective image filtering | 2 | Pre-test program | 3 | 42 | Test different filtering methods
|  |  |  | 7 | Incorrect modeling by generator | 2 | Write code to test output image against expected output | 3 | 42 | Use code from previous error
|  | Generator reproduces old fingerprint instead of making a new one | User cannot make effective use of program for testing purposes | 8 | Ineffective generation procedure | 4 | Write code to ensure output fingerprints differ from original | 3 | 96 | Make the generation procedure more robust
Re-noisification | Add noise and defects to synthetic fingerprint | Inconsistent noise introduction | Noise is not consistent with what would be produced in reality | 6 | Design error (inappropriate noise parameters) | 7 | Control and test different methods of noise production | 5 | 210 | Re-evaluate at next FMEA

## Tables
Probability of Occurrence Ratings
Rating |  | Likelihood of Occurrence
1 | Unlikely | < 0.1%
2 | Low (Few Failures) | < 1 %
3 |  | < 5%
4 | Moderate (Occasional Failure) | < 10%
5 |  | < 12.5%
6 |  | < 15%
7 | High (Repeated Failure) | < 25%
8 |  | < 33%
9 | Very High (Consistent Failure) | < 50%
10 |  | < 100%
Severity Rating
Rating |  | Description
1 | Minor | No effect
2 |  | Minimal effect
3 |  | Minor effects
4 | Medium | Effects are noticeable but not bad
5 |  | Output may not be desired, but effect is acceptable
6 |  | Output is undesired
7 | Unacceptable | Output is unrecognizable
8 |  | Major problems unacceptable output / Sporadic failure
9 |  | Program crashes
10 |  | Program does not run / Immediate program failure
Control Effectiveness Rating
Rating |  | Description
1 | Excellent | Failure is eliminated
2 | Very High | Control not 100% effective
3 | High | Chances of failure are minimal
4 | Moderately High | Slight possibility of failure
5 | Acceptable | Failure not totally eliminated but results are acceptable
6 | Low | Most errors are detected but not dealt with
7 | Very Low | Few errors are detected
8 | Poor | Failures are likely to be undetected
9 | Very Poor | Minimal chance of failure detection
10 | Insufficient | Failures are not prevented or detected