## Productivity
This productivity grid was adapted from information in Capers Jones' book, Estimating Software Costs
Hours per FP
Activity | Minimum | Mode | Maximum | Adjusted? | Est. Hours | Adjusted? | Justification
Requirements | 0.38 | 0.75 | 2.64 | 0.75 | 168.165
Prototyping | 0.53 | 0.88 | 5.28 | 0.88 | 197.3136
Architecture | 0.26 | 0.44 | 1.32 | 0.44 | 98.6568
Project Plans | 0.09 | 0.26 | 0.66 | 0.26 | 58.2972
Initial Design | 0.33 | 0.75 | 2.64 | 0.5 | 112.11 | Y | Using existing design patterns
Detailed Design | 0.44 | 0.88 | 5.28 | 0.88 | 197.3136
Design Reviews | 0.33 | 0.59 | 1.76 | 0.59 | 132.2898
Coding | 0.66 | 2.64 | 8.8 | 2.64 | 591.9408
Reuse Acquisition | 0.07 | 0.22 | 0.33 | 0 | 0 | Y | not required for this project
Package Purchase | 0.09 | 0.33 | 0.38 | 0.33 | 73.9926
Code Inspections | 0.44 | 0.88 | 1.76 | 0.88 | 197.3136
Independent verification and validation | 0.66 | 1.06 | 1.76 | 0 | 0 | Y | not required for this project
Configuration Management | 0.04 | 0.08 | 0.13 | 0.08 | 17.9376
Integration | 0.26 | 0.53 | 0.88 | 0.53 | 118.8366
User Documentation | 1.32 | 1.89 | 6.6 | 1.89 | 423.7758
Unit Testing | 0.33 | 0.88 | 1.89 | 0.88 | 197.3136
Function Testing | 0.44 | 0.88 | 5.28 | 0.88 | 197.3136
Integration Testing | 0.33 | 0.75 | 1.76 | 0.75 | 168.165
System Testing | 0.26 | 0.66 | 1.32 | 0.66 | 147.9852
Field Testing (Alpha/Beta testing) | 0.26 | 0.59 | 1.76 | 0.59 | 132.2898
Acceptance Testing | 0.22 | 0.38 | 1.76 | 0.38 | 85.2036
Independent Testing | 0.44 | 0.66 | 1.32 | 0.66 | 147.9852
Quality Assurance | 0.44 | 0.88 | 4.4 | 0.88 | 197.3136
Installation and Training | 0.22 | 0.38 | 0.88 | 0.38 | 85.2036
Project Management | 0.66 | 1.32 | 8.8 | 1.32 | 295.9704
Total hours/FP | 9.5 | 19.56 | 69.39 | 18.03 | 4042.6866
Defect Rate Estimation by RUP Workflow
Rollup by RUP workflow (from above) | Est. Hours |  | Avg. Rate | Adj. Defect Rate | Est. Defects | Adjusted? | Justification
Business Modeling | 408.0804 |  | 0 | 0 | 0
Requirements | 168.165 |  | 1 | 0.2 | 44.844 | Y | Due to stability of requirements in a known space, errors in requirements are kept to a minimum
Analysis and Design | 388.7975 |  | 1.25 | 0.3 | 67.266 | Y | Due to prototype nature, design defects are moot
Implementation | 1119.7547 |  | 1.75 | 1.26 | 282.5172 | Y | Unit testing and some functional testing defects not counted; Sierra assumes developers will unit test and perform preliminary functional testing using test harnesses.
Test | 869.9736 |  | 0.4 | 0.4 | 89.688 |  | Bad fix defects
Deployment | 508.9794 |  | 0.6 | 0.02 | 4.4844 | Y | Documentation defects (errors including online help screens, user documents, etc.) -- Adj down due to very limited UG requirements
Configuration and Change Management | 109.4194 |  | 0 | 0 | 0
Project Management | 295.522 |  | 0 | 0 | 0
Environment | 173.9947 |  | 0 | 0 | 0
Total Hours | 4042.6866 |  | 5 | 2.18 | 488.7996
To use FPA in the budgeting process, an organization needs to know its productivity rates. The productivity rate or project delivery rate is defined as follows: the number of development hours needed on an average to realize one function point.
Functional size (number of function points) multiplied by the expected project productivity rate (expected hours required per function point) provides a basis for the project budget. One should add hours for activities that are not included in the standard productivity rate.
The productivity rates are based upon experiences in earlier, completed projects. As data from Sierra Systems projects in our branch do not cover a large set, benchmark data and regression equations have been used from reliable companies and researchers. In this case, we've used Capers Jones.
The defect rates should be calibrated according to experiences in earlier, completed projects. This data is just beginning to be collected within Sierra. In the absence of our own data, we are using a US average defect rate per function point.
Capers Jones has more than 25 years of experience with software cost estimation. He frequently leads workshops and seminars and is a featured speaker at industry conferences.

## FP Summary
New Development Project Function Point Count
| Project Name: | Sample Project
| Client Name: | Federal Republic of Elbonia
| Partner: | Glenn Briskin
| Branch: | Seattle - Olympia business unit
| Proj Start Date: | 2002-08-01
| Proj End Date: | 2003-04-15
| Project Status | Entering Iterative Transition phase (finished iteration four, entering iteration five)
(at time of count)
| FP Count Type: | Application
| Date of Count: | 2003-03-17
| Counted by: | Nick Malik
| Date of Review: | 2003-03-21
| Reviewed by: | Daniel Condreay
| Count Version: | 2
| Count Description: | Application FP Count of Sample Project
| UFP | Low | Average | High
| ILF's | 14 | 20 | 45
| EIF's | 20 | 7 | 20
| EI's | 9 | 0 | 18
| EO's | 12 | 0 | 14
| EQ's | 27 | 16 | 0
Total Unadjusted Function Points
222
Value Adjustment Factor
1.01
Adjusted Function Points
224.22
Project Productivity Rate (hours per FP)
18.03
Total Effort Estimate (in days)
505.3358
| Hours by RUP Workflow (from productivity page) |  |  |  | Est Hours
| Business Modeling |  |  |  | 408.0804
| Requirements |  |  |  | 168.165
| Analysis and Design |  |  |  | 388.7975
| Implementation |  |  |  | 1119.7547
| Test |  |  |  | 869.9736
| Deployment |  |  |  | 508.9794
| Configuration and Change Management |  |  |  | 109.4194
| Project Management |  |  |  | 295.522
| Environment |  |  |  | 173.9947
| Total Hours |  |  |  | 4042.6866